## FEC Register
9.1 Forward Engineering Considerations Register — CivicConnect
ID | Concern | Why it matters now | Later decision / activity influenced | Information still missing | Risk of ignoring it | Linked FR / NFR / RSK | Owner | Status
FEC-001 | Security, access control and personal information | What the platform holds about students and staff, and who may read it, is being fixed by the requirements baselined now. CON-007 constrains what may be captured and for how long; CFL-002 restricts security-category visibility; CFL-004 is unresolved and DEC-005 defers the retention period. Personal information collected without a lawful basis cannot be repaired by a later design decision — it has to be collected again. | The M2 data model and the separation of identifiable data from aggregated statistics; the role and permission design behind SCP-012; audit and least-privilege review; the scope of security testing at M3; the platform decision in DEC-003. | Retention guidance from STK-009 or a documented institutional standard; the authoritative campus role model behind STK-007; whether requester identity may be visible to technicians on non-security categories. | Identifiable data accumulates with no rule governing it and the CFL-002 restriction is asserted rather than verified. Realised as RSK-002 and RSK-009. | FR-1.2 · FR-1.3 · FR-1.5 · FR-3.5 · FR-8.6 · NFR-3.3 · NFR-4.1 · NFR-4.2 (OI-05) · NFR-4.4 · CON-006 · CON-007 · CFL-002 · CFL-004 · SCP-012 · SCP-020 · DEC-004 · DEC-005 · RSK-002 · RSK-009 | Christiaan Burger | Open — M1 and M2 influence recorded
FEC-002 | Migration and cut-over from the existing channels | SCP-017 correctly excludes ingestion from email, telephone and WhatsApp, because federating them would preserve the duplication the platform exists to remove. But the exclusion answers a different question from the one the organisation will ask on go-live day: what happens to the requests already open in spreadsheets and mailboxes. That is a cut-over position, and it belongs in the scope baseline now rather than being discovered at deployment. | The scope baseline itself; the release and cut-over plan at M3 and M4; whether any historical data is loaded, and therefore the M2 data model; the backup and recovery approach. | How many requests are open at any time and in what condition the records are; whether STK-004 will re-enter open items manually; whether any historical record must be retained for reporting continuity. | The platform launches empty, staff keep the spreadsheet alive for the backlog, and the fragmentation the project set out to remove survives alongside it. Compounds RSK-001. | No FR or NFR coverage — deliberate under SCP-017; the open backlog at cut-over is unaddressed by any requirement · SCP-017 · STK-004 · RSK-001 · Master Brief s.2.1 | Christiaan Burger | Open — carried to M3
FEC-003 | Testability and measurable acceptance | CON-005 records that every quality attribute written now creates a later obligation to produce evidence, and that vague quality language cannot be verified. The acceptance test is whether a third party could determine pass or fail without asking the team what was meant — so testability governs how requirements are written today, not how they are checked at M3. | Acceptance test design and test data strategy at M3; the test-reference column of the RTM; the observable seams and controlled transitions the M2 design must expose; how many quality attributes the schedule can actually support verifying. | The service-level target that would make 'overdue' in SCP-011 testable; realistic request volumes and concurrent staff numbers; whether representative test data can be obtained or must be synthesised. | Requirements that read well and cannot be verified, breaking the source-to-test traceability the module assesses. Realised as RSK-003, RSK-010 and RSK-011. | FR-8.3 · FR-8.4 (OI-02) · NFR-1.2 · NFR-2.1 · NFR-2.2 · NFR-2.3 · NFR-2.5 · CON-005 · SCP-011 · SCP-008 · DEC-007 · RSK-003 · RSK-010 | Christiaan Burger | Open — partly addressed at M2
FEC-004 | Technology availability in the institutional environment | CON-008 records that Belgium Campus does not guarantee that any chosen language, framework, service or platform is available or supported. DEC-002 already names environment verification as evidence required before the stack is committed. The concern matters now because CON-002 leaves no schedule for discovering an incompatibility after the architecture is fixed. | Technology selection and architecture at M2; the development and test environment definition; the realistic learning curve under CON-004; whether the fallback stack can meet the same quality attributes. | What is actually installed and permitted on the BC Desktop platform; whether external services are reachable from the institutional network; which candidate stacks the team can support with three part-time members. | A technically sound choice proves undeliverable in the available environment and the architecture is reworked with no schedule left to absorb it. Realised as RSK-007. | NFR-1.1 (OI-07) · NFR-1.3 · CON-008 · CON-004 · CON-002 · DEC-002 · RSK-007 | Christiaan Burger | Addressed at M2 — residual in RSK-007
FEC-005 | Deployment platform, audit retention, backup and recovery | DEC-003 already identifies the tension: the cost constraint favours a free tier, but free tiers commonly omit audit log retention, backups and private networking that CON-006 and CON-007 require. Two scope items are deferred behind this decision. Availability and recoverability expectations are meaningless until the environment is known, yet the quality attributes that assume them are being baselined now. | The hosting decision at M2; the staging and production environment definition and rollback plan at M3; the audit trail behind SCP-008; whether SCP-014 and SCP-015 can be brought back into scope. | Documented free-tier limits for candidate platforms covering audit retention, backup and private networking; whether the institution will host; who operates the platform after handover. | Availability and audit commitments made against a platform that cannot support them, with SCP-014 and SCP-015 blocked indefinitely behind an unmade decision. Realised as RSK-008. | NFR-1.4 (OI-06) · NFR-1.5 · NFR-1.6 · NFR-2.5 · DEC-003 · CON-003 · CON-006 · CON-007 · SCP-014 · SCP-015 · RSK-008 | Christiaan Burger | Addressed at M2 — residual in RSK-019, RSK-020
FEC-006 | Observability, audit trail and operational accountability | Weak accountability for status changes is one of the named failures the platform exists to fix, and SCP-008 already commits to recording the acting user on every transition. Whether that record is queryable, retained and trustworthy is what turns it from a stored field into evidence — and that is a requirement-level question, not an implementation detail. | Audit logging and the status-transition model at M2; monitoring, health checks and incident response at M3; the service-performance reporting STK-005 depends on; the retention rule that will eventually govern the audit trail. | How long an audit record must be kept and whether it is subject to the same retention rule as request data; which transitions STK-005 actually reports on; what the platform in DEC-003 will retain by default. | Status changes that cannot be attributed after the fact, and oversight reporting that reproduces the accountability gap in a new system. Related to RSK-002 and RSK-008. | FR-5.4 · FR-6.3 · FR-6.7 · FR-7.3 · NFR-1.4 · NFR-3.6 · NFR-4.5 · SCP-008 · SCP-011 · STK-005 · CON-007 · DEC-003 · RSK-008 | Christiaan Burger | Open — M1 and M2 influence recorded
FEC-007 | Operational cost and sustainability after handover | CON-003 requires free-tier limits and likely operational cost beyond the educational context to be identified, and records that the hosting decision cannot be made on price alone. SCP-014 and SCP-015 are both deferred on cost grounds. A requirement that assumes unlimited notifications or attachments commits STK-008 to an expense nobody has agreed, and the commitment is made by the wording of the requirement rather than by the later build. | The hosting and service decision at M2; whether SCP-014 and SCP-015 return to scope and on what terms; retention periods, which drive storage cost; the final cost review at M4. | Any budget STK-008 will carry after the educational context ends; expected request volume per month; notification channel costs beyond the free tier. | A platform that satisfies its requirements and cannot be afforded to run once the free tiers no longer apply. Realised as RSK-008 and blocks SCP-014 and SCP-015. | NFR-1.4 · NFR-1.5 · NFR-2.5 · CON-003 · STK-008 · DEC-003 · SCP-014 · SCP-015 · RSK-008 | Christiaan Burger | Open — ask outstanding

## FEC Influence
9.2 Influence on the current baseline
FEC ref | What it changed in this baseline | Artefact affected | Ask to A / B
FEC-001 | Access control entered the scope baseline as SCP-012 even though it is not a listed business capability, because the CFL-002 resolution made it functional rather than administrative; DEC-004 records it as architecturally significant; the retention period was deferred in DEC-005 rather than guessed, and SCP-020 was deferred as a direct consequence. | SCP-012 · SCP-020 · DEC-004 · DEC-005 | Already done by A — cite it in §9.2 as evidence, no further ask.
FEC-002 | SCP-017 records the exclusion of channel ingestion with its engineering reason rather than leaving it unstated. The cut-over position for requests already open is still missing. | SCP-017 | A: add a scope row for existing open requests at go-live — in scope, deferred or excluded, with the evidence required.
FEC-003 | CON-005 was recorded with the implication that every quality attribute creates a later evidence obligation, and DEC-007 explicitly hands Member B a measurable mobile-viewport usability obligation rather than a design intention. | CON-005 · DEC-007 | B: DONE — measurement basis carried on all 22 NFRs. OUTSTANDING — no DEC logged for the SCP-011 service-level target; it now exists only as FR-8.4 / AC-FR-8.4 / OI-02.
FEC-004 | CON-008 was recorded as a constraint in its own right, and DEC-002 was deferred with environment verification named as the evidence required before the stack is committed. | CON-008 · DEC-002 | A: PART DONE — DEC-002 names the evidence required and an owner. OUTSTANDING — still no date.
FEC-005 | DEC-003 was deferred on the ground that free tiers omit audit retention, backup and private networking — a deployment concern shaping an M1 decision rather than an M2 one — and SCP-014 and SCP-015 were deferred behind it. | DEC-003 · SCP-014 · SCP-015 | A: PART DONE — DEC-003 names the free-tier evidence required. OUTSTANDING — still no date.
FEC-006 | SCP-008 specifies controlled status transitions with the acting user recorded, which places the audit requirement in the scope baseline rather than leaving accountability to implementation. | SCP-008 | B: DONE — AC-FR-6.3, AC-FR-6.7, AC-NFR-1.4 and AC-NFR-3.6 make the audit expectation testable. Cite in §9.2, no further ask.
FEC-007 | CON-003 records that the hosting decision cannot be made on price alone, and both cost-bearing scope items were deferred pending cost evidence rather than assumed affordable. | CON-003 · SCP-014 · SCP-015 | A: document likely operational cost beyond the educational context as part of the DEC-003 evidence.

## M2 Influence
9.3 Influence at Milestone 2 — what each consideration changed in the architecture, data, technology and design decisions
Added at v0.3 (30/09/2026, C. Burger). The M1 influence record on the previous sheet is preserved unchanged.
FEC ref | M2 decisions it shaped | What it changed at M2 | Still open — carried to M3 | Status at M2
FEC-001 | ASR-01, ASR-03, DEC-012, DEC-014, DEC-017, PROC-001 | Authorisation became the most influential architectural driver (PED §6A.3.3): closed layers and three enforcement points against one rule set. Identifiable request data is held apart from non-identifying aggregates (Requests vs Reporting modules), so retention (DEC-017, PROC-001) can act on one without the other. | CFL-002 still Proposed (C-01, RSK-009), so the field-level serialiser rule is unconfirmed. Encryption at rest (NFR-3.7) is an open evidence item. | Open — influence recorded at M2
FEC-002 | — (no M2 decision) | No M2 decision changed the cut-over position. The data model carries campusId on every collection, so a later bulk load of open requests would not need a migration. | The scope position on requests already open at go-live is still outstanding. Carried to the M3/M4 release and cut-over plan. | Open — carried to M3
FEC-003 | ASR-01 to ASR-06, DEC-011, DEC-012, CI (#52) | Every ASR is stated as a measurable scenario (PED §6A.3.1). DEC-012 chose the enforcement form that can be asserted automatically (route-table test), and DEC-011 made a transition testable by asserting publication. The suite runs without a database, and CI runs it on every pull request. | The service-level target behind "overdue" (C-02, RSK-003); load evidence for NFR-2.1 and NFR-2.4 at M3. | Open — partly addressed
FEC-004 | DEC-002 | DEC-002 closed on a stack the team can support (CON-004), with Node 22 as the stated minimum. The application builds and its tests run on team machines and on a hosted CI runner. | Availability on the BC Desktop image is still not evidenced; the React client version is recorded when the client is scaffolded. | Addressed at M2 — residual carried by RSK-007 (re-scored)
FEC-005 | DEC-003, DEC-010, DEC-011, DEC-017, ASR-06 | DEC-003 separated application hosting (Hostinger VPS) from the managed database (Atlas), which resolved the M1 conflict between cost and audit retention. DEC-010 closed on an operated 12-hourly backup, and DEC-017 gave audit records their own retention purpose (≥ 90 days). DEC-011 means SCP-014 can return as a new subscriber without editing reviewed transition code, so its deferral costs no rework. | Hostinger plan and cost (DEC-003 evidence E1); confirmation of the institutional backup server; the paid-tier upgrade trigger. | Addressed at M2 — residual carried by RSK-019, RSK-020; RSK-008 closed
FEC-006 | ASR-02, DEC-011, DEC-016, DB-01 | The audit write sits below the application in an Atlas trigger (CON-015), history is append-only at three layers (DB-01), and the status change and history entry are one unit of work (DEC-016). Review of PR #62 (B-2) caught audit rows losing the actor role before merge. | Trigger deployment, suspension alerting (RSK-018) and the health endpoint (NFR-1.6) are M3 work. | Open — influence recorded at M2
FEC-007 | DEC-003, DEC-010, DEC-011, ASR-06 | The team kept a free cluster in production with a stated upgrade trigger (DEC-010, RSK-019) and chose one deployable unit to keep operating effort within CON-004 (ASR-06). DEC-011 keeps SCP-014 cheap to add later. | Likely operational cost beyond the educational context is still not documented for STK-008. | Open — ask outstanding