## Scope Baseline
Scope Baseline
Capabilities classified in scope, deferred or out of scope for the M1 baseline, with justification and source
ID | Type | Item / capability | Classification | Justification | Source | Defend in presentation? | Baseline summary
SCP-001 | PRODUCT | Submit a service request with category, location and description | IN SCOPE | Minimum requester capability required by the Master Brief; the core of the business need | Master Brief s.3, STK-001 | No | In scope | 12
SCP-002 | PRODUCT | Controlled category mechanism | IN SCOPE | Required capability; reporting in SCP-011 and triage in SCP-006 both depend on controlled categories rather than free text | Master Brief s.3, STK-004, STK-005 | No | Deferred | 4
SCP-003 | PRODUCT | View status and history of own requests | IN SCOPE | Directly addresses the visibility problem identified in the scenario | Master Brief s.3, STK-001 | No | Out of scope | 4
SCP-004 | PRODUCT | Feedback when a request is accepted, rejected, updated or completed | IN SCOPE | Required capability; delivered as in-application feedback only (see SCP-014 for notifications) | Master Brief s.3, STK-001 | No | Total items | 20
SCP-005 | PRODUCT | Staff view of requests relevant to their authorisation | IN SCOPE | Required staff capability and the point at which authorisation becomes functional rather than administrative | Master Brief s.3, STK-002, STK-003 | No
SCP-006 | PRODUCT | Search, filter and sort requests | IN SCOPE | Required staff capability; addresses the prioritisation difficulty described in the scenario | Master Brief s.3, STK-004 | No
SCP-007 | PRODUCT | Assign or accept responsibility for a request | IN SCOPE | Required staff capability; implements the assignment model agreed in CFL-003 | Master Brief s.3, CFL-003 | No
SCP-008 | PRODUCT | Controlled status transitions with recorded acting user | IN SCOPE | Required staff capability; the recorded actor is what supplies the accountability the current process lacks | Master Brief s.3, s.2, STK-005 | No
SCP-009 | PRODUCT | Record actions, comments and resolution information | IN SCOPE | Required staff capability; creates the single controlled lifecycle record the scenario identifies as missing | Master Brief s.3 | No
SCP-010 | PRODUCT | Resolve or close requests where authorised | IN SCOPE | Required staff capability | Master Brief s.3 | No
SCP-011 | PRODUCT | Management view of open, overdue, resolved and closed requests by category and status | IN SCOPE | Required management capability; the reporting need behind CFL-001 | Master Brief s.3, STK-005 | No
SCP-012 | PRODUCT | Authentication and role-based access control | IN SCOPE | Not listed as a business capability but made necessary by the CFL-002 resolution and CON-006; without it the restricted handling of security requests cannot be delivered | CFL-002, CON-006, STK-007 | Yes
SCP-013 | PRODUCT | Native mobile application | OUT OF SCOPE | A responsive web interface satisfies the stated access need within CON-002 and CON-004. A native build adds a second toolchain, store release process and test matrix with no additional evidenced stakeholder benefit at M1. | CON-002, CON-004 | Yes
SCP-014 | PRODUCT | Email or push notification of status changes | DEFERRED | Valuable to STK-001 but depends on a delivery service whose cost and free-tier limits are unknown until the platform decision in M2. In-application feedback (SCP-004) meets the minimum capability in the interim. | CON-003, DEC-003 | No
SCP-015 | PRODUCT | Photograph attachments on a request | DEFERRED | Would materially improve fault triage, but introduces file storage cost, malware scanning and additional personal-information handling under CON-007. Deferred pending the platform and retention decisions. | CON-003, CON-007 | No
SCP-016 | PRODUCT | Integration with existing campus systems (student records, HR, asset register) | OUT OF SCOPE | No evidence is currently available that institutional APIs exist or would be made accessible to a student project. Committing to an integration the team cannot verify would create unmanageable dependency risk. | CON-008, CON-002 | No
SCP-017 | PRODUCT | Ingestion of requests from existing email, telephone or WhatsApp channels | OUT OF SCOPE | The business need is to replace fragmented channels with a single controlled record, not to federate them. Ingestion would preserve the duplication the platform exists to remove. | Master Brief s.2, s.2.1 | No
SCP-018 | PRODUCT | Technician scheduling, rostering or workload balancing | OUT OF SCOPE | Not a stated capability and not raised by any identified stakeholder; would substantially expand the domain model under a fixed schedule | CON-001, CON-002 | No
SCP-019 | PRODUCT | Multi-campus or multi-tenant operation | DEFERRED | Single-campus operation satisfies the current stakeholders. Recorded as deferred rather than excluded so that the M2 data model does not foreclose it unnecessarily. | CON-002 | No
SCP-020 | PRODUCT | Automated enforcement of the data retention period | DEFERRED | The retention period itself is undecided (DEC-005). Automating enforcement before the rule exists would encode an unverified assumption. | CFL-004, DEC-005 | No