## Open Items
Open Items & Assumptions
Gaps, derived requirements and unvalidated figures carried by this baseline. Recorded rather than resolved by invention — Master Brief s.23 values honest limitations above unsupported claims of completeness
ID | Type | Item | Affects | What is needed to close it | Raised with | Status
OI-01 | Traceability gap | STILL OPEN at v0.2. Master Brief s.3 lists 'View full request details' as a minimum staff capability. Member A's 09/09/2026 baseline adds SCP-021 but no SCP for this capability, so the gap is unchanged. FR-4.2 remains traced provisionally to SCP-005. | FR-4.2 | Member A confirms whether the capability is intentionally merged into SCP-005, or adds an SCP ID for it. | B → A | Open
OI-02 | Derived requirement | STILL OPEN at v0.2. FR-8.4 (target resolution time per category) is not stated in the scope baseline. SCP-011 requires overdue requests to be identified, which cannot be computed without a target. No new SCP addresses it. | FR-8.4 | Member A confirms as an addition to SCP-011, or the team records it as new scope through the Appendix E change process. | B → A | Open
OI-03 | Derived requirement | STILL OPEN at v0.2. FR-9.1 (category administration) is not stated in the scope baseline. SCP-002 commits to a 'controlled category mechanism', which implies a maintained list; without administration every category change becomes a code release. | FR-9.1 | Member A confirms as within SCP-002, or the team records it as new scope through the Appendix E change process. | B → A | Open
OI-04 | Unvalidated assumption | PARTIALLY CLOSED at v0.2. The concurrency figure is CLOSED: CON-010 supplies 100 concurrent users on client authority, replacing the team's 30. Still open are the response-time targets (3 s, 2 s, 5 s) and the 99% availability figure, which remain team assumptions and each create an M3 verification obligation under CON-005. | NFR-2.1, NFR-2.3, NFR-2.4, NFR-2.5 | Confirm response-time and availability expectations with STK-005 and STK-010 before M3 planning commits effort to them. | B | Open (reduced)
OI-05 | Blocked by deferred decision | CLOSED at v0.3. DEC-005 closed at M2 and set the personal-information retention period at one month, so NFR-4.2 now states a figure and is no longer blocked. The item is closed on a different basis from the one recorded against it: neither guidance from the information officer nor a documented institutional retention standard was obtained, and the period was set as a team judgement. That residual is carried forward as OI-12 rather than closed with this item. | NFR-4.2, SCP-020 | No further action on this item. NFR-4.2 requires an acceptance criterion, and SCP-020 remains deferred with an interim manual procedure recorded in the scope baseline. | A (owns DEC-005) | Closed at v0.3
OI-06 | Interim value | UPDATED and ESCALATED at v0.3. Both decisions this item waited on have closed, and the closure of DEC-005 inverts the assumption the item rests on. The 90-day retention in NFR-1.4 was chosen deliberately shorter than any likely POPIA retention period so that it would not pre-empt DEC-005. DEC-005 has now set the personal-information retention period at one month. Where the data retained under NFR-1.4, NFR-1.9 (CON-015 trigger audit) or NFR-1.11 (CON-014 performance logging) contains personal information as defined under CON-007, a 90-day retention exceeds the one-month rule rather than sitting inside it, and the two commitments contradict. DEC-003 has also closed, so the log retention available on the selected services is now determinable rather than unknown. | NFR-1.4, NFR-1.9, NFR-1.11, NFR-4.2, NFR-4.5, DEC-005 | Determine, for each of NFR-1.4, NFR-1.9 and NFR-1.11, whether the data retained contains personal information under CON-007. Where it does, reconcile the figure against the one-month rule through controlled change under Master Brief s.14, amending whichever commitment is wrong rather than leaving both in the baseline. Record the log retention actually available on the cluster tier selected under DEC-010. | B, with C on risk; A for the controlled change | Open - escalated
OI-07 | Unvalidated assumption | UPDATED at v0.3. The action recorded against this item was to confirm the browser set before the M2 technology decision committed to a client-side framework. DEC-002 has now closed and committed to React without that confirmation, so the sequencing this item asked for did not occur. The assumption is therefore carried into the architecture rather than resolved ahead of it. CON-008 continues to state that no given environment is guaranteed available or supported. | NFR-1.1, DEC-002 | Confirm the browser set on the BC Desktop standard image before the M2 technology decision commits to a client-side framework. | B, with A for the DEC-002 consequence | Open
OI-08 | Identifier stability breach | NEW at v0.2. Member A's baseline reassigns SCP-017, SCP-018 and SCP-019 to different capabilities and removes two previously-baselined exclusions: 'Financial processing, procurement or billing' and 'Bulk import of historical requests'. Member B's requirements are unaffected because only SCP-016 is referenced from that range, but any document citing SCP-017, SCP-018 or SCP-019 now cites a different capability than when it was written. | Project Charter §3.2 and §3.3; any M2 artefact citing those IDs | Confirm whether the renumber was deliberate. If so, record it as a controlled change with a supersession note so the previous meanings stay recoverable. The Charter scope section needs correcting either way. | B → A; C for document control | Open
OI-09 | Deliberate non-derivation | NEW at v0.2. SCP-021 (project charter, WBS, project timeline) is classified type PROJECT, not PRODUCT. No functional requirement is derived from it because it is not a capability of the system under construction. Recorded explicitly so the absence reads as a decision rather than an omission. | SCP-021 | No action required. Raised so Member B can defend the absence under questioning. | B | Closed — recorded
OI-10 | Assumption conflict | UPDATED at v0.3. The conflict recorded at v0.2 between CON-010 (100 concurrent users), NFR-2.2 (10 000 requests) and the Charter benefit model (3 000 requests per year) is unchanged. DEC-002 adds a fourth figure to reconcile: free clusters of the selected managed database service limit total data storage to 0.5 GB, which bounds how many requests with their history and audit records can be retained at all. The storage limit and the one-month retention period set by DEC-005 work in the same direction, so they may resolve the conflict rather than deepen it, but the arithmetic has not been done. | NFR-2.2, Charter s.6.3 benefit derivation, DEC-002, DEC-010 | Establish the actual user population and annual request volume with STK-005 and STK-010. Separately, estimate the storage a single request and its history consume, and check that figure against the 0.5 GB free-tier limit and the one-month retention period before the cluster tier is fixed under DEC-010. | B, and PM for the Charter; A for DEC-010 | Open
OI-11 | Deliberate non-derivation | NEW at v0.2. STK-010's primary need is evidence of controlled engineering rather than merely working software. That is a process obligation on the team, not a property of the system, so it is deliberately not expressed as an NFR. It is discharged through Member C's governance evidence and the Charter QA section. | STK-010 | No action on the requirements baseline. Confirm Member C carries it in the governance evidence. | B → C | Closed — recorded
OI-12 | Unvalidated assumption | NEW at v0.3. DEC-005 sets the personal-information retention period at one month as a team judgement. The evidence named against the deferment - guidance from the information officer (STK-009) or a documented institutional retention standard - was not obtained. CON-007 requires the retention position to be defensible under POPIA, whose operative obligation is that personal information is not retained for longer than necessary to achieve the purpose it was collected for. A team-selected period is consistent with that obligation but is not evidence of it, so the figure is recorded as an assumption rather than as a validated value. | NFR-4.2, AC-NFR-4.2, SCP-020, DEC-005, RSK-002 | Confirm the period with STK-009, or adopt and cite a documented institutional retention standard. If neither is obtainable before M3, record the figure explicitly as a team position in the NFR-4.2 measurement basis so that it is not read as stakeholder-validated. | A (owns DEC-005), raised with C for the risk register | Open
OI-01, OI-02, OI-03 and OI-08 are requirements work exposing gaps and instability in the scope baseline. That is traceability doing its job: it is only useful if it can fail. Raise them as GitHub issues against Member A under the DEC-008 branching model rather than resolving them silently here. OI-09 and OI-11 are closed by being recorded: they document deliberate non-derivations so that a missing requirement reads as a decision.