## Open Items
Open Items & Assumptions
Gaps, derived requirements and unvalidated figures carried by this baseline. Recorded rather than resolved by invention — Master Brief s.23 values honest limitations above unsupported claims of completeness ¦ Version 0.6 (12/10/2026). Adds OI-17 (the read endpoint refuses the whole read of a security-category request to non-Security-Officer staff, which is wider than FR-1.5's three restricted fields), OI-18 (whether a blank or whitespace-only reason counts as a recorded reason under FR-6.6) and OI-19 (DEC-003 names the test environment's Atlas project civicconnect-test, but the test cluster's host and the integration-test guard use civicconnecttest), all raised by E. Lindsay; OI-01 to OI-16 unchanged. Version 0.5 (30/09/2026). Adds OI-16 (FR-1.5 against FR-3.5/FR-3.6: whether a requester may see their own description on a security-category request), raised by E. Lindsay; OI-01 to OI-15 unchanged. Version 0.4 (30/09/2026). Adds OI-14 (reportingCounts reconciliation, owner R. van der Merwe for M3) and OI-15 (transition model confirmation, including whether a reopened-then-resolved request satisfies FR-6.5), both raised in PR #62 (E. Lindsay) and its review (R. van der Merwe). OI-01 to OI-13 are unchanged from v0.3. Version 0.3 (29/09/2026). Consolidates the M2 updates drafted by E. Lindsay (OI-05 closed; OI-06 escalated; OI-07, OI-10 updated; OI-12 raised), first committed inside the file named Open_Items_v0.2 (archived in Outdated/ and carrying those v0.3 labels), with the DEC-017 and storage updates by R. van der Merwe (OI-06 closed, OI-10 reduced, OI-13 raised). No separately committed v0.2 content exists in the repository.
ID | Type | Item | Affects | What is needed to close it | Raised with | Status
OI-01 | Traceability gap | STILL OPEN at v0.2. Master Brief s.3 lists 'View full request details' as a minimum staff capability. Member A's 09/09/2026 baseline adds SCP-021 but no SCP for this capability, so the gap is unchanged. FR-4.2 remains traced provisionally to SCP-005. | FR-4.2 | Member A confirms whether the capability is intentionally merged into SCP-005, or adds an SCP ID for it. | B → A | Open
OI-02 | Derived requirement | STILL OPEN at v0.2. FR-8.4 (target resolution time per category) is not stated in the scope baseline. SCP-011 requires overdue requests to be identified, which cannot be computed without a target. No new SCP addresses it. | FR-8.4 | Member A confirms as an addition to SCP-011, or the team records it as new scope through the Appendix E change process. | B → A | Open
OI-03 | Derived requirement | STILL OPEN at v0.2. FR-9.1 (category administration) is not stated in the scope baseline. SCP-002 commits to a 'controlled category mechanism', which implies a maintained list; without administration every category change becomes a code release. | FR-9.1 | Member A confirms as within SCP-002, or the team records it as new scope through the Appendix E change process. | B → A | Open
OI-04 | Unvalidated assumption | PARTIALLY CLOSED at v0.2. The concurrency figure is CLOSED: CON-010 supplies 100 concurrent users on client authority, replacing the team's 30. Still open are the response-time targets (3 s, 2 s, 5 s) and the 99% availability figure, which remain team assumptions and each create an M3 verification obligation under CON-005. | NFR-2.1, NFR-2.3, NFR-2.4, NFR-2.5 | Confirm response-time and availability expectations with STK-005 and STK-010 before M3 planning commits effort to them. | B | Open (reduced)
OI-05 | Blocked by deferred decision | CLOSED at v0.3. DEC-005 closed at M2 and set the personal-information retention period at one month, so NFR-4.2 now states a figure and is no longer blocked. The item is closed on a different basis from the one recorded against it: neither guidance from the information officer nor a documented institutional retention standard was obtained, and the period was set as a team judgement. That residual is carried forward as OI-12 rather than closed with this item. | NFR-4.2, SCP-020 | No further action on this item. NFR-4.2 requires an acceptance criterion, and SCP-020 remains deferred with an interim manual procedure recorded in the scope baseline. | A (owns DEC-005) | Closed at v0.3
OI-06 | Interim value | CLOSED at v0.3 by DEC-017 (R. van der Merwe, 29/09/2026). Retention is set per purpose: identifiable request data no longer than 30 days from closure (purpose A, DEC-005/NFR-4.2); auditLog at least 90 days as a separate accountability purpose (purpose B, NFR-1.4/NFR-1.9), permitted by POPIA s.14(1) as a related lawful purpose, with content minimised to identifiers, changed field names and status values so no purpose-A value outlives DEC-005; performance logs (NFR-1.11) contain no personal information and are kept 30 days (purpose D). Neither figure changes. EARLIER v0.3 ENTRY (E. Lindsay, 29/09/2026, first drafted in the file then named Open_Items_v0.2): UPDATED and ESCALATED at v0.3. Both decisions this item waited on have closed, and the closure of DEC-005 inverts the assumption the item rests on. The 90-day retention in NFR-1.4 was chosen deliberately shorter than any likely POPIA retention period so that it would not pre-empt DEC-005. DEC-005 has now set the personal-information retention period at one month. Where the data retained under NFR-1.4, NFR-1.9 (CON-015 trigger audit) or NFR-1.11 (CON-014 performance logging) contains personal information as defined under CON-007, a 90-day retention exceeds the one-month rule rather than sitting inside it, and the two commitments contradict. DEC-003 has also closed, so the log retention available on the selected services is now determinable rather than unknown. | NFR-1.4, NFR-1.9, NFR-1.11, NFR-4.2, NFR-4.5, DEC-005 | No further action on this item. CR-002 carries the measurement-basis changes to NFR-1.4, NFR-1.9 and NFR-4.2 and AC-NFR-4.2 v0.3. Log retention on the selected tier is recorded in DEC-010/DEC-017. Previously required: Determine, for each of NFR-1.4, NFR-1.9 and NFR-1.11, whether the data retained contains personal information under CON-007. Where it does, reconcile the figure against the one-month rule through controlled change under Master Brief s.14, amending whichever commitment is wrong rather than leaving both in the baseline. Record the log retention actually available on the cluster tier selected under DEC-010. | B, with C on risk; A for the controlled change | Closed at v0.3
OI-07 | Unvalidated assumption | UPDATED at v0.3. The action recorded against this item was to confirm the browser set before the M2 technology decision committed to a client-side framework. DEC-002 has now closed and committed to React without that confirmation, so the sequencing this item asked for did not occur. The assumption is therefore carried into the architecture rather than resolved ahead of it. CON-008 continues to state that no given environment is guaranteed available or supported. | NFR-1.1, DEC-002 | Confirm the browser set on the BC Desktop standard image before the M2 technology decision commits to a client-side framework. | B, with A for the DEC-002 consequence | Open
OI-08 | Identifier stability breach | NEW at v0.2. Member A's baseline reassigns SCP-017, SCP-018 and SCP-019 to different capabilities and removes two previously-baselined exclusions: 'Financial processing, procurement or billing' and 'Bulk import of historical requests'. Member B's requirements are unaffected because only SCP-016 is referenced from that range, but any document citing SCP-017, SCP-018 or SCP-019 now cites a different capability than when it was written. | Project Charter §3.2 and §3.3; any M2 artefact citing those IDs | Confirm whether the renumber was deliberate. If so, record it as a controlled change with a supersession note so the previous meanings stay recoverable. The Charter scope section needs correcting either way. | B → A; C for document control | Open
OI-09 | Deliberate non-derivation | NEW at v0.2. SCP-021 (project charter, WBS, project timeline) is classified type PROJECT, not PRODUCT. No functional requirement is derived from it because it is not a capability of the system under construction. Recorded explicitly so the absence reads as a decision rather than an omission. | SCP-021 | No action required. Raised so Member B can defend the absence under questioning. | B | Closed — recorded
OI-10 | Assumption conflict | PARTIALLY CLOSED at v0.3: the storage arithmetic is done (data baseline s.7: ~44 MB persistent growth per 10 000 requests against the 0.5 GB free-cluster limit, so storage does not bind; throughput does, see RSK-019). The population and annual-volume conflict remains open. EARLIER v0.3 ENTRY (E. Lindsay, 29/09/2026, first drafted in the file then named Open_Items_v0.2): UPDATED at v0.3. The conflict recorded at v0.2 between CON-010 (100 concurrent users), NFR-2.2 (10 000 requests) and the Charter benefit model (3 000 requests per year) is unchanged. DEC-002 adds a fourth figure to reconcile: free clusters of the selected managed database service limit total data storage to 0.5 GB, which bounds how many requests with their history and audit records can be retained at all. The storage limit and the one-month retention period set by DEC-005 work in the same direction, so they may resolve the conflict rather than deepen it, but the arithmetic has not been done. | NFR-2.2, Charter s.6.3 benefit derivation, DEC-002, DEC-010 | Establish the actual user population and annual request volume with STK-005 and STK-010. Separately, estimate the storage a single request and its history consume, and check that figure against the 0.5 GB free-tier limit and the one-month retention period before the cluster tier is fixed under DEC-010. | B, and PM for the Charter; A for DEC-010 | Open (reduced)
OI-11 | Deliberate non-derivation | NEW at v0.2. STK-010's primary need is evidence of controlled engineering rather than merely working software. That is a process obligation on the team, not a property of the system, so it is deliberately not expressed as an NFR. It is discharged through Member C's governance evidence and the Charter QA section. | STK-010 | No action on the requirements baseline. Confirm Member C carries it in the governance evidence. | B → C | Closed — recorded
OI-12 | Unvalidated assumption | NEW at v0.3. DEC-005 sets the personal-information retention period at one month as a team judgement. The evidence named against the deferment - guidance from the information officer (STK-009) or a documented institutional retention standard - was not obtained. CON-007 requires the retention position to be defensible under POPIA, whose operative obligation is that personal information is not retained for longer than necessary to achieve the purpose it was collected for. A team-selected period is consistent with that obligation but is not evidence of it, so the figure is recorded as an assumption rather than as a validated value. | NFR-4.2, AC-NFR-4.2, SCP-020, DEC-005, RSK-002 | Confirm the period with STK-009, or adopt and cite a documented institutional retention standard. If neither is obtainable before M3, record the figure explicitly as a team position in the NFR-4.2 measurement basis so that it is not read as stakeholder-validated. | A (owns DEC-005), raised with C for the risk register | Open
OI-13 | Requirements conflict | NEW at v0.3. FR-6.7 requires that no user, including an Administrator, may alter or delete a recorded status transition, assignment or comment entry. NFR-4.2 (with DEC-005 and DEC-017) requires identifiable data, including comment text and actor identity on those same entries, to be removed no later than 30 days after closure; PROC-001 does this by nulling personal fields in requestHistory under a temporary, audited database credential. Read literally, the two baselined requirements cannot both hold after day 30. | FR-6.7, AC-FR-6.7, NFR-4.2, AC-NFR-4.2, DEC-017, PROC-001, SCP-020 | Approve CR-003: FR-6.7 text and AC-FR-6.7 unchanged; its measurement basis states that immutability applies to every system interface and application credential, and that end-of-retention removal of personal fields under PROC-001 (status values, change types, roles, timestamps and sequence preserved) is not an alteration of lifecycle content. | B → A for the controlled change | Open
OI-14 | Unassigned work | NEW at v0.4. The reportingCounts projection is maintained by a DEC-011 subscriber that runs after commit and is not retried, so a failed or missed call leaves the counts drifting from requests with no recovery path (review comment R-17). DEC-010 also requires the counts to be rebuilt after any restore from mongodump. No reconciliation job exists. Raised by E. Lindsay in PR #62; recorded there as M3 work without an owner. Ownership accepted by R. van der Merwe (Member B) as a data and persistence concern. | FR-8.1, FR-8.2, FR-8.6, DEC-010, DEC-011, DEC-017, reportingCounts (data baseline) | M3: implement a reconciliation job that rebuilds reportingCounts from requests (categoryId and status survive PROC-001 anonymisation under DEC-017, so the rebuild remains exact after anonymisation). Reuse scripts/backup/consistency-check.js so restore and routine reconciliation share one implementation; run it after every restore and on a schedule; verify against a seeded data set with a deliberately drifted count. | A (PR #62) → B; owner B for M3 | Open — owner B, target M3
OI-15 | Design proposal awaiting confirmation | NEW at v0.4. FR-6.2 requires a controlled transition model but does not state its contents, and FR-6.4 requires role restriction without naming the mapping. The model in src/domain/requestStatus.js (PR #62) is a design proposal. Open question (raised in the PR #62 review): the model permits Resolved → In Progress (reopen), and resolution.* is not cleared on reopen, so a later move back to Resolved without a new summary is accepted because the retained resolution.summary satisfies the FR-6.5 check. FR-6.5 does not say whether resolution information recorded before a reopen still counts. The same proposal carries four judgements beyond the requirements text: (1) Administrator is not a transition role (FR-1.4, FR-9.x); (2) only a Security Officer may act on a security-category request, a reading of CFL-002 'restricted visibility and handling' wider than FR-1.5's three fields; (3) mayViewRequest therefore narrows FR-4.6, which presents unassigned requests to the Coordinator without a security exception; (4) request:assign includes the Manager, where FR-5.1 names only the Coordinator. | FR-6.2, FR-6.4, FR-6.5, FR-7.5, FR-1.4, FR-1.5, FR-4.6, FR-5.1, CFL-002, requests.resolution (data baseline s.3.2), src/domain/requestStatus.js, src/domain/accessRules.js | Team decides the reopen rule: either (a) the original summary satisfies FR-6.5, recorded in the FR-6.5 measurement basis; or (b) a reopen clears resolution.* (the prior summary remains in requestHistory) so a fresh summary is required before Resolved, and the transition model is adjusted. Add a test for whichever is chosen. Team confirms or rejects judgements (1) to (4); any that changes a requirement goes through controlled change. CFL-002 remains Proposed (condition C-01), so (2) and (3) also depend on STK-006 confirmation. | A (owns the transition model) → B, C | Open
OI-16 | Requirements conflict | FR-1.5 restricts the description, comment history and action history of a security-category request to the Security Officer role. Read literally this withholds the description from the requester who submitted it, which FR-3.5 and FR-3.6 both appear to assume they can see. The requirements do not settle it. | FR-1.5, FR-3.5, FR-3.6, NFR-4.4, DEC-012 (enforcement point 3), CFL-002 | Target: To be settled with the CFL-002 confirmation, before the response serialiser is built (M3). Owner: R. van der Merwe (register), with STK-006 to confirm. | Raised 30/09/2026 by E. Lindsay. Related: Condition C-01, RSK-009, OI-15 | Open
OI-17 | Design proposal awaiting confirmation | GET /api/v1/requests/{id} (provisional, FR-4.2 pending OI-01) returns only reference, status and version. For a security-category request it refuses the whole read with 403 to any staff user who is not a Security Officer, because it applies the existing mayViewRequest rule. FR-1.5 restricts only "the description, comment history and action history" of such a request to the Security Officer role; reference, status and version are none of those. Refusing the whole read is therefore an inference beyond the requirement — the same shape as OI-15, and the same rule as its judgements (2) and (3), now reachable over HTTP. Current behaviour errs MORE restrictive than the requirement, which is the safe direction, so nothing changes in the code today. | FR-1.5, FR-4.2 (OI-01), FR-4.6, CFL-002, OI-15 (judgements 2 and 3), OI-16, DEC-012 (enforcement point 3), src/domain/accessRules.js (mayViewRequest), src/services/requestQueryService.js | Team decides whether a non-Security-Officer staff user may read the non-restricted fields of a security-category request. (a) Keep refusing the whole read: record it as the confirmed reading of CFL-002's "restricted visibility and handling", which settles OI-15 judgement (2) for reads. (b) Allow the read and withhold only FR-1.5's three fields: this needs DEC-012 enforcement point 3 (the response serialiser), so it follows CFL-002 / OI-16. Either way, the read tests are updated to the decision and negative-verified. | Raised 12/10/2026 by E. Lindsay. Related: OI-15, OI-16, CFL-002, Condition C-01 | Open
OI-18 | Traceability gap | FR-6.6 requires closing or rejecting “with a recorded reason”. AC-FR-6.6 tests a transition “submitted without a reason, and then resubmitted with one”, and DEC-015 §4 maps “reason missing on close/reject” to 422. None of them says whether a blank or whitespace-only reason is “a reason”. The implementation treats any non-empty string as a recorded reason (statusTransitionService.js, hasReason: Boolean(reason)), so a reason of a single space is accepted and stored. The recorded reason is what FR-3.4 feeds back to the requester on rejection (FR-6.6 note). Not decided from the code. | FR-6.6, AC-FR-6.6, FR-3.4, DEC-015 §4, src/services/statusTransitionService.js, src/domain/requestStatus.js (REASON_REQUIRED) | Team decides whether a reason must contain non-whitespace text. If yes: a controlled change to AC-FR-6.6 (or its measure) stating it, a defect for the current behaviour, a server-side check returning 422 as for a missing reason, and a negative-verified test. If no: record that any non-empty string satisfies FR-6.6, and close. | Raised 12/10/2026 by E. Lindsay. Related: FR-3.4, DEC-015 | Open
OI-19 | Traceability gap | DEC-003 v0.2’s environment map names the test environment “civicconnect-test” (Atlas project / cluster column). The integration-test guard (tests/integration/_harness.js, PR #88) runs only when the host in MONGODB_URI contains “civicconnecttest”, with no hyphen, and the test cluster’s actual host does contain that unhyphenated spelling: a read-only run on 2026-10-12 used the real test connection string and passed the same host check (docs/evidence/M3-indexes/listIndexes_refused_civicconnect-app.txt; the host itself is not recorded). The run evidence (docs/evidence/M3_API_Test_Run.txt) gives the project as “CivicConnect-Test”. So the record has one spelling and the environment and code use another. DEC-003’s column also doesn’t separate the Atlas project name from the cluster name, and the host comes from the cluster name. A guard written from DEC-003’s spelling would refuse the real test cluster; one written from the host doesn’t trace to the record. The URI itself is not in the repository and was not read. | DEC-003 (environment map, Test row), tests/integration/_harness.js (TEST_CLUSTER_MARKER), M3 API Test Specification §3.2, docs/evidence/M3_API_Test_Run.txt, the planned E2E guard (DEC-019); related: DEF-006 | Record the test environment’s Atlas project name and cluster name separately, as they exist, in a new DEC-003 version (the deploy-procedure gap from DEC-019 and the index step from TD-004 could go in the same version). Then the guard’s marker cites that record, and the E2E guard uses the same value. If the cluster is renamed instead, the guard and the evidence change with it. | Raised 12/10/2026 by E. Lindsay. Related: R. van der Merwe (DEC-003 owner), DEF-006, DEC-019 | Open
OI-01, OI-02, OI-03 and OI-08 are requirements work exposing gaps and instability in the scope baseline. That is traceability doing its job: it is only useful if it can fail. Raise them as GitHub issues against Member A under the DEC-008 branching model rather than resolving them silently here. OI-09 and OI-11 are closed by being recorded: they document deliberate non-derivations so that a missing requirement reads as a decision.