## Defect Register
Defect Register
M3 brief §12: "Maintain a simple defect record: defect -> severity/impact -> status -> fix -> regression evidence where corrected." §15: "Known defects ¦ Open/closed ¦ Business impact ¦ Block or residual risk". Each row has a stable DEF identifier the RTM Defect/Status column can cite. Identifiers are never reused or renumbered; a closed defect stays in the register.
Severity and priority scales below are a TEAM PROCESS CONVENTION, not a domain value from the requirements.
S1 Critical — an acceptance criterion cannot be met, or data lost, corrupted or exposed. Blocks release.
S2 Major — a requirement only partly met, or a documented control does not hold in some case. Release only with the limitation recorded.
S3 Minor — incorrect behaviour with a workaround, or code and record disagree.
S4 Trivial — cosmetic or documentation only.
P1 before the M3 release candidate · P2 before M4 · P3 backlog.
ID | Date raised | Found by | Defect | Affects (requirement / artefact) | Severity | Business impact | Priority | Status | Fix | Fix reference | Regression evidence | Block or residual risk | Owner
DEF-001 |  | Review (M3 Phase 0 records) | Risk Register V0.6: the band conditional formatting covered I3:I17 and the filter covered B2:P15, so RSK-016 to RSK-020 had no band colour and fell outside the filter. | Risk Register (controlled artefact) | S3 | High-priority risks RSK-016 and RSK-020 were not visibly banded, and filtering the register silently omitted five risks. A review relying on the filter would miss them. | P1 | Closed | Ranges extended to I3:I23 and B2:P23 in Risk Register V0.7, covering every row including RSK-021. | Commit 6598b58 (Risk Register V0.7) | Read-back of the V0.7 workbook: formatting range I3:I23, filter B2:P23, zero existing cells changed. No automated regression test exists for workbook formatting. | Residual: a future row appended beyond row 23 needs the ranges extended again. No release block. | Ethan
DEF-002 |  | Review (OpenAPI update) | docs/api/openapi.yaml did not list INTERNAL_ERROR in Problem.code, although the error handler has always sent it for every unrecognised error. | DEC-015, docs/api/openapi.yaml, src/middleware/errorHandler.js | S3 | A client generated from the contract would treat the 500 problem's code as undocumented. The contract understated what the API returns. | P1 | Closed | INTERNAL_ERROR added to Problem.code with the three new Phase 0 codes. A contract test now derives the code set from src/errors.js and the error handler at run time and requires it to equal the documented set. | Commit 70d1825 (fix); commit 4921f4c (regression test) | tests/openapiContract.test.js. Negative verification NV-25 (removing INTERNAL_ERROR fails the test) and NV-26 (adding an undocumented error type fails the test), docs/evidence/M3-P0/. | None. No release block. | Ethan
DEF-003 |  | Self-review before first commit | Near miss: tests/config.test.js held a literal credential-shaped MongoDB URI (fake value) that the CI secret scan could flag. Caught before it was committed. | NFR-3.5, CI secret-scan job | S4 | None realised. Had it been committed, a secret-scan failure would have blocked merging, and the string would sit permanently in history (NFR-3.5 is assessed across the full history). | P1 | Closed | The fake credential is assembled at run time from parts, so no credential-shaped literal exists in the file. | Commit 70d1825 (the literal was replaced before that first commit) | git log --all -S on the literal returns no commit on any ref (checked 11/10/2026). Gitleaks full-history secret scan passed on the code PR #83 at commit bc867f3 (GitHub Actions run 38152562066, job "Secret scan (full history)", 11/10/2026). | None. No history exposure. | Ethan