## Open Items
Open Items & Assumptions
Gaps, derived requirements and unvalidated figures carried by this baseline. Recorded rather than resolved by invention — Master Brief s.23 values honest limitations above unsupported claims of completeness
ID | Type | Item | Affects | What is needed to close it | Raised with | Status
OI-01 | Traceability gap | STILL OPEN at v0.2. Master Brief s.3 lists 'View full request details' as a minimum staff capability. Member A's 09/09/2026 baseline adds SCP-021 but no SCP for this capability, so the gap is unchanged. FR-4.2 remains traced provisionally to SCP-005. | FR-4.2 | Member A confirms whether the capability is intentionally merged into SCP-005, or adds an SCP ID for it. | B → A | Open
OI-02 | Derived requirement | STILL OPEN at v0.2. FR-8.4 (target resolution time per category) is not stated in the scope baseline. SCP-011 requires overdue requests to be identified, which cannot be computed without a target. No new SCP addresses it. | FR-8.4 | Member A confirms as an addition to SCP-011, or the team records it as new scope through the Appendix E change process. | B → A | Open
OI-03 | Derived requirement | STILL OPEN at v0.2. FR-9.1 (category administration) is not stated in the scope baseline. SCP-002 commits to a 'controlled category mechanism', which implies a maintained list; without administration every category change becomes a code release. | FR-9.1 | Member A confirms as within SCP-002, or the team records it as new scope through the Appendix E change process. | B → A | Open
OI-04 | Unvalidated assumption | PARTIALLY CLOSED at v0.2. The concurrency figure is CLOSED: CON-010 supplies 100 concurrent users on client authority, replacing the team's 30. Still open are the response-time targets (3 s, 2 s, 5 s) and the 99% availability figure, which remain team assumptions and each create an M3 verification obligation under CON-005. | NFR-2.1, NFR-2.3, NFR-2.4, NFR-2.5 | Confirm response-time and availability expectations with STK-005 and STK-010 before M3 planning commits effort to them. | B | Open (reduced)
OI-05 | Blocked by deferred decision | STILL BLOCKED at v0.2. NFR-4.2 has no retention figure because DEC-005 defers the personal-information retention period pending guidance from STK-009. DEC-005 remains DEFERRED in Member A's 09/09/2026 log. | NFR-4.2, SCP-020 | Retention guidance from the information officer, or a documented institutional retention standard, as recorded against DEC-005. | A (owns DEC-005) | Blocked
OI-06 | Interim value | The 90-day retention in NFR-1.4 was chosen deliberately shorter than any likely POPIA retention period so it does not pre-empt DEC-005. v0.2 adds two more consumers of retained storage: CON-014 performance logging (NFR-1.11) and CON-015 trigger audit (NFR-1.9). Retention now spans three requirements rather than one. | NFR-1.4, NFR-1.9, NFR-1.11, NFR-4.5 | Revisit once DEC-005 closes and once DEC-003 identifies what log retention the candidate platforms actually provide. | B, with C on risk | Open
OI-07 | Unvalidated assumption | NFR-1.1 names Chrome, Edge and Firefox on Windows. CON-011 now mandates a web application on client authority but names no browser set, and CON-008 still states Belgium Campus does not guarantee any given environment is available or supported. | NFR-1.1 | Confirm the browser set on the BC Desktop standard image before the M2 technology decision commits to a client-side framework. | B | Open
OI-08 | Identifier stability breach | NEW at v0.2. Member A's baseline reassigns SCP-017, SCP-018 and SCP-019 to different capabilities and removes two previously-baselined exclusions: 'Financial processing, procurement or billing' and 'Bulk import of historical requests'. Member B's requirements are unaffected because only SCP-016 is referenced from that range, but any document citing SCP-017, SCP-018 or SCP-019 now cites a different capability than when it was written. | Project Charter §3.2 and §3.3; any M2 artefact citing those IDs | Confirm whether the renumber was deliberate. If so, record it as a controlled change with a supersession note so the previous meanings stay recoverable. The Charter scope section needs correcting either way. | B → A; C for document control | Open
OI-09 | Deliberate non-derivation | NEW at v0.2. SCP-021 (project charter, WBS, project timeline) is classified type PROJECT, not PRODUCT. No functional requirement is derived from it because it is not a capability of the system under construction. Recorded explicitly so the absence reads as a decision rather than an omission. | SCP-021 | No action required. Raised so Member B can defend the absence under questioning. | B | Closed — recorded
OI-10 | Assumption conflict | NEW at v0.2. CON-010 sets 100 concurrent users. That is hard to reconcile with the 10 000-request data volume in NFR-2.2 or the 3 000 requests/year assumed in the Project Charter benefit model: a platform serving 100 concurrent users implies a considerably larger institution than either figure describes. At least one of the three is wrong. | NFR-2.2; Charter §6.3 benefit derivation | Establish the actual user population and annual request volume with STK-005 and STK-010. This affects Member B's NFR and the Charter's ROI simultaneously. | B, and PM for the Charter | Open
OI-11 | Deliberate non-derivation | NEW at v0.2. STK-010's primary need is evidence of controlled engineering rather than merely working software. That is a process obligation on the team, not a property of the system, so it is deliberately not expressed as an NFR. It is discharged through Member C's governance evidence and the Charter QA section. | STK-010 | No action on the requirements baseline. Confirm Member C carries it in the governance evidence. | B → C | Closed — recorded
OI-01, OI-02, OI-03 and OI-08 are requirements work exposing gaps and instability in the scope baseline. That is traceability doing its job: it is only useful if it can fail. Raise them as GitHub issues against Member A under the DEC-008 branching model rather than resolving them silently here. OI-09 and OI-11 are closed by being recorded: they document deliberate non-derivations so that a missing requirement reads as a decision.