## Technical Debt Register
Technical Debt Register
Known shortcuts and unimplemented baselined rules, why each was accepted, what it costs while unpaid, and what repaying it involves. A debt item is never deleted: a repaid item is marked Repaid with its PR.
ID | Date raised | Description | Why incurred | Requirements / decisions affected | Consequence while unpaid | Containment and verification now | Repayment | Repayment trigger | Owner | Status | Linked artefacts
TD-001 |  | The DEC-011 subscribers (NotificationSubscriber, ReportingProjectionSubscriber) are not registered in the composed application. A status transition publishes request.status.changed to no listeners. | M3 Phase 0 is reachability only. No notification or reportingCounts repository exists, and the reporting projection has no reconciliation path (OI-14), so wiring it now would create counts that drift with no recovery. | FR-3.4, FR-3.5, FR-8.1, FR-8.2, SCP-004, DEC-011, OI-14 | No in-app notifications are created and reportingCounts is not maintained. DEC-011's mechanism is live but unexercised in the running application. Transitions are unaffected: publish() with no listeners is a no-op that cannot throw. | A test asserts listSubscriptions() is empty once the application is composed, and cites TD-001. Registering a subscriber breaks that test, which forces this entry to be updated in the same change. | Build the notification and reportingCounts repositories; call registerSubscribers() from the composition root; resolve OI-14 (reconciliation) before attaching the projection; replace the empty-registry test with one asserting both registrations. | When FR-3.4 or FR-8.x enters M3 scope after Phase 0. | Unassigned | Open | DEC-011 · OI-14 · DEC-018
TD-002 |  | FR-1.6 effective permissions are specified (DB-01 §3.7) as union(role permissions, group permissions), and effective category authorisation as union(user, groups), resolved by the guard. Not implemented: accessRules.js evaluates OPERATION_RULES by role and the user's own categoryAuthorisations only. Groups are modelled and never evaluated. | Implementing the union changes authorisation rules, which belong in src/domain/accessRules.js under DEC-012, not in the Phase 0 session work. Recorded as debt, not an open item, because the rule is specified, not undecided. | FR-1.6, AC-FR-1.6, CON-019, DEC-012, DB-01 §3.7 | Group membership grants nothing. An Administrator can define groups (once FR-1.6 administration exists) with no effect on access. When repaid, a further consequence follows: a group permission can admit a non-staff user at DEC-012 enforcement point 1 (the route guard), but enforcement point 2 (mayActOnRequest) is role-based and refuses every non-staff actor, so for non-staff users the union would admit at one point and refuse at the next. Points 1 and 2 would disagree. Recorded here as a consequence, not as an open item. | req.actor already carries groupIds (DEC-018 §4), read from users on every request. Security-category protection (FR-1.5) holds today ONLY because groups cannot carry roles and both mayActOnRequest and mayViewRequest check the Security Officer role BEFORE category authorisation. DB-01 §3.7 does not itself scope the union away from security categories. Enforced by test, not by memory: two TD-002 constraint tests in tests/authorisationGuard.test.js fail if the role-first check is removed from either predicate (commit 4921f4c; negative verification NV-23, NV-24). | The rule change is inside src/domain/accessRules.js under DEC-012. groupIds alone does not carry permissions: the groups documents must also be read per request (no caching, NFR-2.7) by a component with repository access, and where that read happens is part of the repayment. CONSTRAINT ON REPAYMENT: the role-first Security Officer check must be preserved in both predicates, and the TD-002 constraint tests must still pass unchanged. The accessRules tests gain group cases, negative-verified. | When FR-1.6 group administration is built, or before CON-019 testing, whichever comes first. | Unassigned | Open | DB-01 §3.7 · DEC-012 · DEC-018