## Open Items
Open Items & Assumptions
Gaps, derived requirements and unvalidated figures carried by this baseline. Recorded rather than resolved by invention — Master Brief s.23 values honest limitations above unsupported claims of completeness ¦ Version 0.8 (17/10/2026, M4 final pass, R. van der Merwe). Adds columns I (Final status, M4: Closed with evidence, or Remains open for future work) and J (the engineering reason and the evidence). Every open item is given a final status. OI-05, OI-06, OI-09, OI-11 and OI-19 were closed earlier and are left exactly as they were. Adds two rows for items carried from M2 that are not open items but need a final status here: C-05 (PED Appendix B) and CON-019. E. Lindsay's two proposed items (the missing category list; the Information Officer in AC-NFR-4.5) were not raised in this version. On 18/10/2026 OI-13 was closed with evidence (CR-003 approved, PR #137; J17 in E. Lindsay's wording) and CON-019's final status confirmed from the v4.0-M4-rc evidence. After review (18/10/2026), the reasons for OI-02, OI-03, OI-04, OI-07, OI-14 and OI-18 were brought up to date with the M4 build and the release-candidate results. Columns B to H of every existing row are unchanged. Version 0.7 (13/10/2026). Closes OI-19 (DEC-003 v0.3, PR #92, records the test environment's name, Atlas project and redacted cluster hostname separately, and the integration-test guard cites it), raised by E. Lindsay. Adds OI-21 (DEC-003 places staging and production on a VPS that never existed; found at deployment and resolved for staging only by a disposable Azure VM, with DEC-003 to be superseded), raised by R. van der Merwe. OI-01 to OI-18 and OI-20 unchanged. Version 0.6 (12/10/2026; OI-20 added 13/10/2026). Adds OI-17 (the read endpoint refuses the whole read of a security-category request to non-Security-Officer staff, which is wider than FR-1.5's three restricted fields), OI-18 (whether a blank or whitespace-only reason counts as a recorded reason under FR-6.6), OI-19 (DEC-003 names the test environment's Atlas project civicconnect-test, but the test cluster's host and the integration-test guard use civicconnecttest) and OI-20 (no CI gate inspects content inside non-Office binaries such as images and PDFs; found when an embedded provenance manifest in the three PED architecture figures passed every required check, removed on PR #94), all raised by E. Lindsay; OI-01 to OI-16 unchanged. Version 0.5 (30/09/2026). Adds OI-16 (FR-1.5 against FR-3.5/FR-3.6: whether a requester may see their own description on a security-category request), raised by E. Lindsay; OI-01 to OI-15 unchanged. Version 0.4 (30/09/2026). Adds OI-14 (reportingCounts reconciliation, owner R. van der Merwe for M3) and OI-15 (transition model confirmation, including whether a reopened-then-resolved request satisfies FR-6.5), both raised in PR #62 (E. Lindsay) and its review (R. van der Merwe). OI-01 to OI-13 are unchanged from v0.3. Version 0.3 (29/09/2026). Consolidates the M2 updates drafted by E. Lindsay (OI-05 closed; OI-06 escalated; OI-07, OI-10 updated; OI-12 raised), first committed inside the file named Open_Items_v0.2 (archived in Outdated/ and carrying those v0.3 labels), with the DEC-017 and storage updates by R. van der Merwe (OI-06 closed, OI-10 reduced, OI-13 raised). No separately committed v0.2 content exists in the repository.
ID | Type | Item | Affects | What is needed to close it | Raised with | Status | Final status (M4) | Final reason and evidence (M4)
OI-01 | Traceability gap | STILL OPEN at v0.2. Master Brief s.3 lists 'View full request details' as a minimum staff capability. Member A's 09/09/2026 baseline adds SCP-021 but no SCP for this capability, so the gap is unchanged. FR-4.2 remains traced provisionally to SCP-005. | FR-4.2 | Member A confirms whether the capability is intentionally merged into SCP-005, or adds an SCP ID for it. | B → A | Open | Remains open for future work | No SCP ID was added for 'view full request details', and FR-4.2 is still traced provisionally to SCP-005 (Scope Baseline v0.3). A request-detail read exists (GET /api/v1/requests/{id}, OI-17), but the scope-baseline gap this item records was never corrected by Member A. Evidence: Scope Baseline v0.3; RTM v0.11, FR-4.2 row.
OI-02 | Derived requirement | STILL OPEN at v0.2. FR-8.4 (target resolution time per category) is not stated in the scope baseline. SCP-011 requires overdue requests to be identified, which cannot be computed without a target. No new SCP addresses it. | FR-8.4 | Member A confirms as an addition to SCP-011, or the team records it as new scope through the Appendix E change process. | B → A | Open | Remains open for future work | FR-8.4 is now built and Met at the frozen build 6408ab7: the Manager sets a category's target resolution time, it is shown on the Categories page (DEF-028 fixed), and overdue requests are identified against it (FR-8.3 Met). What this item asks is still not done: Member A never confirmed FR-8.4 as part of SCP-011 or recorded it as new scope, so FR-8.4 stays Proposed. Evidence: RTM v0.11 (FR-8.3, FR-8.4); Scope Baseline v0.3.
OI-03 | Derived requirement | STILL OPEN at v0.2. FR-9.1 (category administration) is not stated in the scope baseline. SCP-002 commits to a 'controlled category mechanism', which implies a maintained list; without administration every category change becomes a code release. | FR-9.1 | Member A confirms as within SCP-002, or the team records it as new scope through the Appendix E change process. | B → A | Open | Remains open for future work | FR-9.1 is now built and Met at 6408ab7: the Administrator deactivates a category from the user interface, and it is no longer offered on the New request form (E2E-7; DEF-025 fixed). Reactivation is not built. What this item asks is still not done: FR-9.1 was never confirmed as within SCP-002 or recorded as new scope. Evidence: RTM v0.11 (FR-9.1); Scope Baseline v0.3.
OI-04 | Unvalidated assumption | PARTIALLY CLOSED at v0.2. The concurrency figure is CLOSED: CON-010 supplies 100 concurrent users on client authority, replacing the team's 30. Still open are the response-time targets (3 s, 2 s, 5 s) and the 99% availability figure, which remain team assumptions and each create an M3 verification obligation under CON-005. | NFR-2.1, NFR-2.3, NFR-2.4, NFR-2.5 | Confirm response-time and availability expectations with STK-005 and STK-010 before M3 planning commits effort to them. | B | Open (reduced) | Remains open for future work | The response-time targets (3 s, 2 s, 5 s) and the 99 % availability figure were never confirmed with STK-005 or STK-010. At M3, NFR-2.4 passed on staging (15/10/2026, a workload without submissions). At the release candidate (18/10/2026), NFR-2.4 and NFR-2.1 were run on staging and are Not Met (DEF-032: counter contention under concurrent submissions). NFR-2.3 and NFR-2.5 were not measured. Evidence: docs/evidence/M4-perf/; RTM v0.11 (NFR-2.1, NFR-2.4).
OI-05 | Blocked by deferred decision | CLOSED at v0.3. DEC-005 closed at M2 and set the personal-information retention period at one month, so NFR-4.2 now states a figure and is no longer blocked. The item is closed on a different basis from the one recorded against it: neither guidance from the information officer nor a documented institutional retention standard was obtained, and the period was set as a team judgement. That residual is carried forward as OI-12 rather than closed with this item. | NFR-4.2, SCP-020 | No further action on this item. NFR-4.2 requires an acceptance criterion, and SCP-020 remains deferred with an interim manual procedure recorded in the scope baseline. | A (owns DEC-005) | Closed at v0.3
OI-06 | Interim value | CLOSED at v0.3 by DEC-017 (R. van der Merwe, 29/09/2026). Retention is set per purpose: identifiable request data no longer than 30 days from closure (purpose A, DEC-005/NFR-4.2); auditLog at least 90 days as a separate accountability purpose (purpose B, NFR-1.4/NFR-1.9), permitted by POPIA s.14(1) as a related lawful purpose, with content minimised to identifiers, changed field names and status values so no purpose-A value outlives DEC-005; performance logs (NFR-1.11) contain no personal information and are kept 30 days (purpose D). Neither figure changes. EARLIER v0.3 ENTRY (E. Lindsay, 29/09/2026, first drafted in the file then named Open_Items_v0.2): UPDATED and ESCALATED at v0.3. Both decisions this item waited on have closed, and the closure of DEC-005 inverts the assumption the item rests on. The 90-day retention in NFR-1.4 was chosen deliberately shorter than any likely POPIA retention period so that it would not pre-empt DEC-005. DEC-005 has now set the personal-information retention period at one month. Where the data retained under NFR-1.4, NFR-1.9 (CON-015 trigger audit) or NFR-1.11 (CON-014 performance logging) contains personal information as defined under CON-007, a 90-day retention exceeds the one-month rule rather than sitting inside it, and the two commitments contradict. DEC-003 has also closed, so the log retention available on the selected services is now determinable rather than unknown. | NFR-1.4, NFR-1.9, NFR-1.11, NFR-4.2, NFR-4.5, DEC-005 | No further action on this item. CR-002 carries the measurement-basis changes to NFR-1.4, NFR-1.9 and NFR-4.2 and AC-NFR-4.2 v0.3. Log retention on the selected tier is recorded in DEC-010/DEC-017. Previously required: Determine, for each of NFR-1.4, NFR-1.9 and NFR-1.11, whether the data retained contains personal information under CON-007. Where it does, reconcile the figure against the one-month rule through controlled change under Master Brief s.14, amending whichever commitment is wrong rather than leaving both in the baseline. Record the log retention actually available on the cluster tier selected under DEC-010. | B, with C on risk; A for the controlled change | Closed at v0.3
OI-07 | Unvalidated assumption | UPDATED at v0.3. The action recorded against this item was to confirm the browser set before the M2 technology decision committed to a client-side framework. DEC-002 has now closed and committed to React without that confirmation, so the sequencing this item asked for did not occur. The assumption is therefore carried into the architecture rather than resolved ahead of it. CON-008 continues to state that no given environment is guaranteed available or supported. | NFR-1.1, DEC-002 | Confirm the browser set on the BC Desktop standard image before the M2 technology decision commits to a client-side framework. | B, with A for the DEC-002 consequence | Open | Remains open for future work | The BC Desktop browser set was never confirmed. At M4 the E2E journeys ran 56 of 56 in four browser projects (Chromium, Chrome, Edge and Playwright's Firefox) at 6408ab7. AC-NFR-1.1 is Partially Met: prior releases and Mozilla's release Firefox are not shown, and without the BC image's set the coverage target itself is unconfirmed. Evidence: e2e/playwright.config.js; docs/evidence/M4-build/E2E_run_2026-10-17_final_four_browsers_run2.txt; RTM v0.11 (NFR-1.1).
OI-08 | Identifier stability breach | NEW at v0.2. Member A's baseline reassigns SCP-017, SCP-018 and SCP-019 to different capabilities and removes two previously-baselined exclusions: 'Financial processing, procurement or billing' and 'Bulk import of historical requests'. Member B's requirements are unaffected because only SCP-016 is referenced from that range, but any document citing SCP-017, SCP-018 or SCP-019 now cites a different capability than when it was written. | Project Charter §3.2 and §3.3; any M2 artefact citing those IDs | Confirm whether the renumber was deliberate. If so, record it as a controlled change with a supersession note so the previous meanings stay recoverable. The Charter scope section needs correcting either way. | B → A; C for document control | Open | Remains open for future work | The SCP-017 to SCP-019 renumbering was never confirmed as deliberate, and no controlled change records it: CR-001 to CR-004 cover other items. Documents citing those IDs may still cite a different capability than when they were written. Evidence: docs/change/ (no CR for the renumbering).
OI-09 | Deliberate non-derivation | NEW at v0.2. SCP-021 (project charter, WBS, project timeline) is classified type PROJECT, not PRODUCT. No functional requirement is derived from it because it is not a capability of the system under construction. Recorded explicitly so the absence reads as a decision rather than an omission. | SCP-021 | No action required. Raised so Member B can defend the absence under questioning. | B | Closed — recorded
OI-10 | Assumption conflict | PARTIALLY CLOSED at v0.3: the storage arithmetic is done (data baseline s.7: ~44 MB persistent growth per 10 000 requests against the 0.5 GB free-cluster limit, so storage does not bind; throughput does, see RSK-019). The population and annual-volume conflict remains open. EARLIER v0.3 ENTRY (E. Lindsay, 29/09/2026, first drafted in the file then named Open_Items_v0.2): UPDATED at v0.3. The conflict recorded at v0.2 between CON-010 (100 concurrent users), NFR-2.2 (10 000 requests) and the Charter benefit model (3 000 requests per year) is unchanged. DEC-002 adds a fourth figure to reconcile: free clusters of the selected managed database service limit total data storage to 0.5 GB, which bounds how many requests with their history and audit records can be retained at all. The storage limit and the one-month retention period set by DEC-005 work in the same direction, so they may resolve the conflict rather than deepen it, but the arithmetic has not been done. | NFR-2.2, Charter s.6.3 benefit derivation, DEC-002, DEC-010 | Establish the actual user population and annual request volume with STK-005 and STK-010. Separately, estimate the storage a single request and its history consume, and check that figure against the 0.5 GB free-tier limit and the one-month retention period before the cluster tier is fixed under DEC-010. | B, and PM for the Charter; A for DEC-010 | Open (reduced) | Remains open for future work | The storage arithmetic is done (data baseline s.7). The actual population and annual request volume were never established with STK-005 or STK-010. The NFR-2.4 test used CON-010's 100 concurrent users, which the client gave. Evidence: data baseline s.7; PED M3.8.
OI-11 | Deliberate non-derivation | NEW at v0.2. STK-010's primary need is evidence of controlled engineering rather than merely working software. That is a process obligation on the team, not a property of the system, so it is deliberately not expressed as an NFR. It is discharged through Member C's governance evidence and the Charter QA section. | STK-010 | No action on the requirements baseline. Confirm Member C carries it in the governance evidence. | B → C | Closed — recorded
OI-12 | Unvalidated assumption | NEW at v0.3. DEC-005 sets the personal-information retention period at one month as a team judgement. The evidence named against the deferment - guidance from the information officer (STK-009) or a documented institutional retention standard - was not obtained. CON-007 requires the retention position to be defensible under POPIA, whose operative obligation is that personal information is not retained for longer than necessary to achieve the purpose it was collected for. A team-selected period is consistent with that obligation but is not evidence of it, so the figure is recorded as an assumption rather than as a validated value. | NFR-4.2, AC-NFR-4.2, SCP-020, DEC-005, RSK-002 | Confirm the period with STK-009, or adopt and cite a documented institutional retention standard. If neither is obtainable before M3, record the figure explicitly as a team position in the NFR-4.2 measurement basis so that it is not read as stakeholder-validated. | A (owns DEC-005), raised with C for the risk register | Open | Remains open for future work | The one-month period was never confirmed with STK-009, and no institutional retention standard was cited. It stays a team position, and the NFR-4.2 basis says so. Evidence: Decision Log v0.10, DEC-005.
OI-13 | Requirements conflict | NEW at v0.3. FR-6.7 requires that no user, including an Administrator, may alter or delete a recorded status transition, assignment or comment entry. NFR-4.2 (with DEC-005 and DEC-017) requires identifiable data, including comment text and actor identity on those same entries, to be removed no later than 30 days after closure; PROC-001 does this by nulling personal fields in requestHistory under a temporary, audited database credential. Read literally, the two baselined requirements cannot both hold after day 30. | FR-6.7, AC-FR-6.7, NFR-4.2, AC-NFR-4.2, DEC-017, PROC-001, SCP-020 | Approve CR-003: FR-6.7 text and AC-FR-6.7 unchanged; its measurement basis states that immutability applies to every system interface and application credential, and that end-of-retention removal of personal fields under PROC-001 (status values, change types, roles, timestamps and sequence preserved) is not an alteration of lifecycle content. | B → A for the controlled change | Open | Closed with evidence | Closed by CR-003, approved 17/10/2026 by the team (E. Lindsay, Team Lead) at M4 closure; not validated with a client stakeholder. FR-6.7's measurement basis (Functional Requirements v0.3) now states the one sanctioned exception: removing personal fields at the end of the retention period under PROC-001 is not an alteration of lifecycle content (status values, change types, roles, timestamps and sequence are preserved), and it is executed only by a temporary, audited database credential outside the system's interfaces. FR-6.7's text and AC-FR-6.7 are unchanged, so FR-6.7 and NFR-4.2 no longer conflict as written. PROC-001 is still run by hand only (scripts/retention/proc-001-anonymise.js; SCP-020 deferred). Evidence: docs/change/CR-003_FR-6.7_Retention_Exception_v0.2.md; PED v4.0.
OI-14 | Unassigned work | NEW at v0.4. The reportingCounts projection is maintained by a DEC-011 subscriber that runs after commit and is not retried, so a failed or missed call leaves the counts drifting from requests with no recovery path (review comment R-17). DEC-010 also requires the counts to be rebuilt after any restore from mongodump. No reconciliation job exists. Raised by E. Lindsay in PR #62; recorded there as M3 work without an owner. Ownership accepted by R. van der Merwe (Member B) as a data and persistence concern. | FR-8.1, FR-8.2, FR-8.6, DEC-010, DEC-011, DEC-017, reportingCounts (data baseline) | M3: implement a reconciliation job that rebuilds reportingCounts from requests (categoryId and status survive PROC-001 anonymisation under DEC-017, so the rebuild remains exact after anonymisation). Reuse scripts/backup/consistency-check.js so restore and routine reconciliation share one implementation; run it after every restore and on a schedule; verify against a seeded data set with a deliberately drifted count. | A (PR #62) → B; owner B for M3 | Open — owner B, target M3 | Remains open for future work | No reconciliation job was built, and the M3 target was missed (owner R. van der Merwe). The reportingCounts projection is not registered (TD-001 partly repaid: the notification subscriber is), and the management view built at M4 counts from requests directly (FR-8.1 to FR-8.6 Met at 6408ab7), so there is no projection to drift or rebuild. The item stays open because DEC-011 and DEC-010 still describe the projection and its rebuild after a restore. scripts/backup/consistency-check.js exists for the restore path but is not scheduled. Evidence: RTM v0.11 (FR-8.1 to FR-8.6); TD-001 (Technical Debt Register v0.4); src/composition.js.
OI-15 | Design proposal awaiting confirmation | NEW at v0.4. FR-6.2 requires a controlled transition model but does not state its contents, and FR-6.4 requires role restriction without naming the mapping. The model in src/domain/requestStatus.js (PR #62) is a design proposal. Open question (raised in the PR #62 review): the model permits Resolved → In Progress (reopen), and resolution.* is not cleared on reopen, so a later move back to Resolved without a new summary is accepted because the retained resolution.summary satisfies the FR-6.5 check. FR-6.5 does not say whether resolution information recorded before a reopen still counts. The same proposal carries four judgements beyond the requirements text: (1) Administrator is not a transition role (FR-1.4, FR-9.x); (2) only a Security Officer may act on a security-category request, a reading of CFL-002 'restricted visibility and handling' wider than FR-1.5's three fields; (3) mayViewRequest therefore narrows FR-4.6, which presents unassigned requests to the Coordinator without a security exception; (4) request:assign includes the Manager, where FR-5.1 names only the Coordinator. | FR-6.2, FR-6.4, FR-6.5, FR-7.5, FR-1.4, FR-1.5, FR-4.6, FR-5.1, CFL-002, requests.resolution (data baseline s.3.2), src/domain/requestStatus.js, src/domain/accessRules.js | Team decides the reopen rule: either (a) the original summary satisfies FR-6.5, recorded in the FR-6.5 measurement basis; or (b) a reopen clears resolution.* (the prior summary remains in requestHistory) so a fresh summary is required before Resolved, and the transition model is adjusted. Add a test for whichever is chosen. Team confirms or rejects judgements (1) to (4); any that changes a requirement goes through controlled change. CFL-002 remains Proposed (condition C-01), so (2) and (3) also depend on STK-006 confirmation. | A (owns the transition model) → B, C | Open | Remains open for future work | The transition model is still a team proposal, not confirmed with the stakeholders. The reopen rule (FR-6.5) and judgements (1) to (4) were not decided. DEF-019's fix corrected the Administrator test's title to cite this item rather than FR-6.7 (PR #123), so the record no longer presents the proposal as baselined. Evidence: src/domain/requestStatus.js header; PR #123.
OI-16 | Requirements conflict | FR-1.5 restricts the description, comment history and action history of a security-category request to the Security Officer role. Read literally this withholds the description from the requester who submitted it, which FR-3.5 and FR-3.6 both appear to assume they can see. The requirements do not settle it. | FR-1.5, FR-3.5, FR-3.6, NFR-4.4, DEC-012 (enforcement point 3), CFL-002 | Target: To be settled with the CFL-002 confirmation, before the response serialiser is built (M3). Owner: R. van der Merwe (register), with STK-006 to confirm. | Raised 30/09/2026 by E. Lindsay. Related: Condition C-01, RSK-009, OI-15 | Open | Remains open for future work | CFL-002 was never confirmed with STK-006, so the conflict between FR-1.5 and FR-3.5/FR-3.6 is unsettled, and the response serialiser (DEC-012 point 3) was not built. Evidence: Decision Log v0.10, DEC-012; Stakeholder Conflicts v0.1, CFL-002.
OI-17 | Design proposal awaiting confirmation | GET /api/v1/requests/{id} (provisional, FR-4.2 pending OI-01) returns only reference, status and version. For a security-category request it refuses the whole read with 403 to any staff user who is not a Security Officer, because it applies the existing mayViewRequest rule. FR-1.5 restricts only "the description, comment history and action history" of such a request to the Security Officer role; reference, status and version are none of those. Refusing the whole read is therefore an inference beyond the requirement — the same shape as OI-15, and the same rule as its judgements (2) and (3), now reachable over HTTP. Current behaviour errs MORE restrictive than the requirement, which is the safe direction, so nothing changes in the code today. | FR-1.5, FR-4.2 (OI-01), FR-4.6, CFL-002, OI-15 (judgements 2 and 3), OI-16, DEC-012 (enforcement point 3), src/domain/accessRules.js (mayViewRequest), src/services/requestQueryService.js | Team decides whether a non-Security-Officer staff user may read the non-restricted fields of a security-category request. (a) Keep refusing the whole read: record it as the confirmed reading of CFL-002's "restricted visibility and handling", which settles OI-15 judgement (2) for reads. (b) Allow the read and withhold only FR-1.5's three fields: this needs DEC-012 enforcement point 3 (the response serialiser), so it follows CFL-002 / OI-16. Either way, the read tests are updated to the decision and negative-verified. | Raised 12/10/2026 by E. Lindsay. Related: OI-15, OI-16, CFL-002, Condition C-01 | Open | Remains open for future work | Not decided. The whole read of a security-category request is still refused to staff who are not Security Officers: more restrictive than FR-1.5, which is the safe direction. Option (b) needs the serialiser, which waits on OI-16. Evidence: src/domain/accessRules.js (mayViewRequest); Decision Log v0.10, DEC-012.
OI-18 | Traceability gap | FR-6.6 requires closing or rejecting “with a recorded reason”. AC-FR-6.6 tests a transition “submitted without a reason, and then resubmitted with one”, and DEC-015 §4 maps “reason missing on close/reject” to 422. None of them says whether a blank or whitespace-only reason is “a reason”. The implementation treats any non-empty string as a recorded reason (statusTransitionService.js, hasReason: Boolean(reason)), so a reason of a single space is accepted and stored. The recorded reason is what FR-3.4 feeds back to the requester on rejection (FR-6.6 note). Not decided from the code. | FR-6.6, AC-FR-6.6, FR-3.4, DEC-015 §4, src/services/statusTransitionService.js, src/domain/requestStatus.js (REASON_REQUIRED) | Team decides whether a reason must contain non-whitespace text. If yes: a controlled change to AC-FR-6.6 (or its measure) stating it, a defect for the current behaviour, a server-side check returning 422 as for a missing reason, and a negative-verified test. If no: record that any non-empty string satisfies FR-6.6, and close. | Raised 12/10/2026 by E. Lindsay. Related: FR-3.4, DEC-015 | Open | Remains open for future work | Not decided. At v4.0-M4-rc, a whitespace-only reason is still accepted: hasReason is Boolean(reason) (src/services/statusTransitionService.js line 83), and the route does not trim it. Consequence: a rejection can carry a reason that tells the requester nothing (FR-3.4). Evidence: that line; AC-FR-6.6.
OI-19 | Traceability gap | CLOSED at v0.7 (13/10/2026). DEC-003 v0.3 (PR #92, merged 13/10/2026) records, in separate columns of its environment map, the test environment's environment name (civicconnect-test), Atlas project (CivicConnect-Test) and cluster hostname (civicconnecttest.[redacted].mongodb.net; the project-specific part is redacted on purpose). tests/integration/_harness.js now cites that record as the source of its marker, and e2e/playwright.config.js uses the harness's rule, so both guards use the recorded value. The cluster's display name in the Atlas UI is not recorded: the guards match the hostname, and its first label is the recorded marker. Original item: DEC-003 v0.2's environment map names the test environment "civicconnect-test" (Atlas project / cluster column). The integration-test guard (tests/integration/_harness.js, PR #88) runs only when the host in MONGODB_URI contains "civicconnecttest", with no hyphen, and the test cluster's actual host does contain that unhyphenated spelling: a read-only run on 2026-10-12 used the real test connection string and passed the same host check (docs/evidence/M3-indexes/listIndexes_refused_civicconnect-app.txt; the host itself is not recorded). The run evidence (docs/evidence/M3_API_Test_Run.txt) gives the project as "CivicConnect-Test". So the record has one spelling and the environment and code use another. DEC-003's column also doesn't separate the Atlas project name from the cluster name, and the host comes from the cluster name. A guard written from DEC-003's spelling would refuse the real test cluster; one written from the host doesn't trace to the record. The URI itself is not in the repository and was not read. | DEC-003 (environment map, Test row), tests/integration/_harness.js (TEST_CLUSTER_MARKER), M3 API Test Specification §3.2, docs/evidence/M3_API_Test_Run.txt, the planned E2E guard (DEC-019); related: DEF-006 | No further action on this item. If the test cluster is renamed or replaced, DEC-003's Test row, the harness marker and the evidence that cites the hostname change together, as the original closing condition required. Original closing condition: Record the test environment's Atlas project name and cluster name separately, as they exist, in a new DEC-003 version (the deploy-procedure gap from DEC-019 and the index step from TD-004 could go in the same version). Then the guard's marker cites that record, and the E2E guard uses the same value. If the cluster is renamed instead, the guard and the evidence change with it. | Raised 12/10/2026 by E. Lindsay. Related: R. van der Merwe (DEC-003 owner), DEF-006, DEC-019 | Closed at v0.7
OI-20 | Unassigned work | No CI gate inspects content inside a binary file other than an Office document. Found on 13/10/2026: the three PED architecture figures (docs/PED/PED/Media/architecture-logical.png, -modules.png, -physical.png, committed in #49 on 29/09/2026) each carried an embedded C2PA provenance manifest (a 5,758-byte caBX chunk). It sat on dev for two weeks and through every required check. The secret scan (ci.yml, NFR-3.5) runs Gitleaks on text and, since #86/#91, on the extracted text of every Office document version. ci.yml itself records that "other binaries (images) are not text containers and are not covered". So a credential, personal information (for example GPS or author fields in a photo's EXIF data) or any other embedded text in an image, PDF or archive would pass unseen. This is the same kind of blind spot as the Office-document gap closed in #86, for the file types that fix did not reach. The metadata in these three files is removed on PR #94 (pixels unchanged). The original files remain in history at 1faf60d. | NFR-3.5, CON-006, .github/workflows/ci.yml (secret-scan job), .github/workflows/secret-scan-all-branches.yml, scripts/ci/extract-office-documents.sh, Team Working Agreement v0.2 §9 (AI use is disclosed in the AI Usage Register), PR #94 | The team decides whether binary metadata is in scope for a gate. If yes: a CI step that lists embedded metadata and text chunks in committed images and PDFs (for example PNG tEXt/iTXt/zTXt/caBX, JPEG EXIF/XMP, PDF document info) and fails on a defined set, shown to fail on a seeded file before it is relied on. Then a Decision Log entry or a ci.yml comment stating what is and is not covered. If no: record the accepted residual in ci.yml and the Risk Register, with a reviewer check for added binaries in the PR template, and close. | Raised 13/10/2026 by E. Lindsay. Related: C. Burger (CI and repository governance), PR #94 | Open | Remains open for future work | No CI gate inspects metadata or text inside images or PDFs. The secret scan covers text and the extracted text of Office documents only, and ci.yml says so. The three figures found on 13/10/2026 were cleaned (PR #94). Evidence: .github/workflows/ci.yml (secret-scan job comments); PR #94.
OI-21 | Unvalidated assumption | NEW at v0.7. A baselined decision rests on an asset that does not exist, found at deployment. DEC-003 (v0.1 to v0.3) puts the application on a Hostinger KVM VPS: its Application host row, the Staging and Production rows of the environment map ("Staging and production share the VPS"), the Atlas access list restricted to "the VPS static IP", and the deploy script run "on the VPS". The Decision Log's DEC-003 row rests on "we have access to the server", and DEC-002 v0.1 assesses its options as "self-hosted on the VPS the team already has under DEC-003". No such VPS ever existed. DEC-003's Evidence still required items 1 (the VPS plan and its cost) and 2 (its static IP) are still outstanding in v0.3, so the record never showed it either. Found on 13/10/2026 by R. van der Merwe when asked to deploy to staging. Resolved for staging only, outside the record: a disposable Azure virtual machine on E. Lindsay's Azure for Students credit (Spain Central, Standard_B2ls_v2, Ubuntu 24.04). It is explicitly not the CTRLWEB VPS, which hosts live client sites. The region was not chosen: the subscription's allowed-regions policy forced it. Consequences: the staging Atlas cluster, not yet created (DEC-003 environment map), must be colocated with the VM, and every performance result measured on staging (NFR-2.1, NFR-2.3, NFR-2.4) must state the region. Staging holds synthetic data only (DEC-003 environment map), so no personal information is placed outside South Africa; that does not carry over to production (CON-007). Production still has no host: DEC-003's Production row also names the VPS, and the Azure VM is disposable. DEC-003 is not edited here; a superseding version is needed. | DEC-003 v0.3 (Application host, Database access, Release & rollback, Deployment procedure, environment map Staging and Production rows, Evidence still required items 1 and 2), DEC-002 v0.1 (options assessment), Decision Log DEC-003 row, NFR-2.1, NFR-2.3, NFR-2.4, CON-003, CON-007 | A superseding DEC-003 version (owner R. van der Merwe) that records the staging host as it exists (provider and subscription, region and the policy that forced it, VM size, OS, that it is disposable, and that it is not the CTRLWEB VPS); the staging Atlas cluster's region, colocated with the VM; the rule that staging performance results state their region; and the production host, or an explicit record that it is not yet decided. DEC-002 v0.1's "the VPS the team already has" and the Decision Log's DEC-003 row are corrected in their next versions. Closes when the superseding DEC-003 is merged. | Raised 13/10/2026 by R. van der Merwe, found when asked to deploy; recorded by E. Lindsay. Related: R. van der Merwe (DEC-003 owner), DEC-002 | Open | Remains open for future work (production host); staging part closed with evidence | Staging: closed. DEC-003 v0.4 (PR #99) records the staging host as it exists. DEC-003 v0.5 (PR #134) accepts non-colocation as a standing staging condition, with both regions stated in every performance result; that replaces this item's colocation clause, which a free cluster in the VM's region could not meet. The Decision Log's DEC-003 row was corrected in v0.9 (PR #114). Production: open. There is no production host, cluster or access list, and CON-007 means production cannot inherit the staging regions. DEC-002 v0.1's 'the VPS the team already has' is not yet corrected. Evidence: DEC-003 v0.5; Decision Log v0.10.
C-05 | Carried from M2 (PED Appendix B condition) | Act on the capacity and schedule finding: Project Charter v0.3 s.4.6 records that the baselined scope could not be delivered in the window at any evidenced productivity rate. A velocity checkpoint was set for the CON-013 gate on 29/09/2026, with a scope-reduction order to be agreed in advance. Not an open item; it is given a final status here so that every carried item has one. | Project Charter v0.3 s.4.6, s.5.2; CON-009, CON-013; RSK-001, RSK-015; M1 scope | Measure velocity at the gate, agree the scope-reduction order before it, and record both in the Decision Log (PED Appendix B). | M1 review; owner R. van der Merwe | Open | Remains open for future work | Never closed. No velocity measurement was taken at the 29/09/2026 gate, and no scope-reduction order was agreed in advance (PED v3.0 Appendix B and M3.10). The consequence it predicted materialised: the committed scope was not delivered in full. The M4 scope completion figure (PED v4.0) is the after-the-fact measurement of that shortfall. It is not the advance control C-05 asked for. Evidence: PED v3.0 Appendix B; PED v4.0 scope completion.
CON-019 | Carried from M2 (constraint not yet evidenced) | The client requires RBAC, user grouping and encryption to be tested adversarially: authorisation is enforced at the server at every entry point, and hiding an interface control is not a restriction. Adversarial testing against a deployed server was planned and not run at M3. Not an open item; it is given a final status here so that every carried item has one. | CON-019, NFR-3.3, ASR-01, DEC-004, DEC-012, RSK-021 | Run adversarial tests against a deployed server, not only locally, covering every entry point, role and restricted field. | M3 (PED v3.0 M3.10); owner C. Burger for the tests | Open | Remains open for future work | Partly evidenced, not met. A route-table test fails CI if a non-public route lacks the guard (NFR-3.3). E2E-2 calls the API directly with a wrong role and is refused with nothing written, but at M3 it ran locally only. Nothing has probed the deployed staging server: no adversarial case ran on staging at v4.0-M4-rc (18/10/2026), where the checks were TLS, the performance log, stored passwords and session and query plans. Login has no throttling (RSK-021, CodeQL #1), and the field-level restriction is not built (OI-16). Encryption at rest is not evidenced (NFR-3.7). Evidence: tests/authorisationGuard.test.js; docs/evidence/M3-e2e/; DEC-003 v0.5.
OI-01, OI-02, OI-03 and OI-08 are requirements work exposing gaps and instability in the scope baseline. That is traceability doing its job: it is only useful if it can fail. Raise them as GitHub issues against Member A under the DEC-008 branching model rather than resolving them silently here. OI-09 and OI-11 are closed by being recorded: they document deliberate non-derivations so that a missing requirement reads as a decision.