## stakeholder-register
Stakeholder Register
Service request platform — stakeholder identification, influence/interest rating and engagement approach
ID | Stakeholder | Relationship to system | Primary need | Influence | Interest | Engagement approach
STK-001 | Student / staff requester | Submits service requests and tracks their own request | Submit a request quickly and know it was received and what is happening to it | Low | High | Interview a sample of requesters: review current email / WhatsApp request history
STK-002 | Facilities / maintenance technician | Resolves physical faults and maintenance requests | See assigned work clearly and update status from where the work is done | Medium | High | Observe current workflow: walkthrough of a typical fault
STK-003 | IT support technician | Resolves IT support requests | Same queue behaviour as facilities, but different categories and turnaround expectations | Medium | High | Interview: compare category and priority needs against STK-002
STK-004 | Service desk coordinator | Triages, categorises and assigns incoming requests | Avoid duplicate and unassigned requests; maintain visibility of the whole queue | Medium | High | Process walkthrough of current triage across email, phone and WhatsApp
STK-005 | Operations manager | Oversight and service performance reporting | Reliable view of open, overdue, resolved and closed work by category | High | High | Interview: confirm which reporting dimensions are actually used
STK-006 | Campus security officer | Handles security-concern requests | Restricted handling and visibility of sensitive security reports | Medium | Medium | Interview: confirm confidentiality expectations for security categories
STK-007 | System administrator | Manages user accounts, roles and permissions | A manageable role model with the ability to onboard and revoke access reliably | Medium | Medium | Interview: review existing institutional account management practice
STK-008 | Campus executive sponsor | Funds and authorises the platform | Improved accountability and service performance without unsustainable operational cost | High | Medium | Periodic milestone review: cost and benefit summary
STK-009 | Information officer / POPIA compliance | Governs handling of personal information | Lawful, auditable handling of student and staff personal information | High | Low | Confirm data handling obligations before baseline
Power / Interest Grid
Influence rated High/Medium is treated as higher influence; Interest rated High is treated as higher interest
HIGHER INFLUENCE | Keep Satisfied |  |  | Manage Closely
| STK-006 · Campus security officer |  |  | STK-002 · Facilities / maintenance technician
| STK-007 · System administrator |  |  | STK-003 · IT support technician
| STK-008 · Campus executive sponsor |  |  | STK-004 · Service desk coordinator
| STK-009 · Information officer / POPIA compliance |  |  | STK-005 · Operations manager
LOWER INFL. | Monitor |  |  | Keep Informed
| None identified |  |  | STK-001 · Student / staff requester
| LOWER INTEREST |  |  | HIGHER INTEREST
Takeaway: every stakeholder identified holds either power or a stake — nobody is safely ignorable.

## stakeholder-conflicts
Stakeholder Conflicts
Competing stakeholder needs, why they cannot both be fully satisfied, and the resulting change in scope or requirements
ID | Stakeholder A | Stakeholder B | Nature of the conflict | Why it cannot simply be satisfied both ways | Status | Resolution (change in scope / requirements) | Affected artefact refs
CFL-001 | STK-001 Student / staff requester | STK-005 Operations manager | Requester needs to submit a request in as few steps as possible; manager needs richly categorised, structured data to report on open, overdue and resolved work by category | Every additional mandatory capture field increases submission effort for the requester. Optional fields produce incomplete data, which weakens the reporting the manager depends on. Both cannot be maximised. | Proposed | Keep the mandatory field set minimal (category, location, description) and prompt for additional detail after submission rather than before. Category remains mandatory because reporting cannot function without it. | STK-001, STK-005
CFL-002 | STK-001 Student / staff requester | STK-006 Campus security officer | Requester expects full visibility of the status and handling of their own request; security officer requires restricted visibility and handling of security-concern reports | Full transparency on a security-category request could expose who is investigating, what action is being taken, or details that compromise the response. Restricting it removes the visibility that the whole platform exists to provide. | Proposed | Security-category requests expose a reduced status set to the requester (received, in progress, closed) with detail and comments restricted to an authorised security role. Drives a role-based access requirement rather than a single shared view. | STK-001, STK-006, STK-007
CFL-003 | STK-002 / STK-003 Technicians | STK-004 Service desk coordinator | Technicians want to select work from a shared queue based on their own location and availability; coordinator needs controlled assignment so that ownership and accountability are unambiguous | Open self-selection produces the same duplication and unclear ownership the current process suffers from. Fully centralised assignment removes the technicians' practical knowledge of what they can actually reach and reduces responsiveness. | Proposed | Coordinator assigns by default; technicians may accept an unassigned request within their own category. Every assignment and status transition records the acting user, so accountability holds under either path. | STK-002, STK-003, STK-004
CFL-004 | STK-005 Operations manager | STK-009 Information officer / POPIA compliance | Manager wants historical request data retained for service-performance analysis; information officer requires personal information to be minimised and not retained longer than necessary | Service-performance trends need history. POPIA requires retention to be justified and limited. Keeping everything indefinitely is not lawful; deleting aggressively destroys the reporting value. | Proposed — retention deferred | Define a retention period for identifiable request data and retain aggregated, non-identifying statistics beyond it. Retention period is deferred pending confirmation from the information officer. | STK-005, STK-009
Open item: the retention period in CFL-004 is deferred pending confirmation from the information officer — all other conflicts have a proposed resolution.

## scope-baseline
Scope Baseline
Capabilities classified in scope, deferred or out of scope for the M1 baseline, with justification and source
ID | Item / capability | Classification | Justification | Source | Defend in presentation?
SCP-001 | Submit a service request with category, location and description | IN SCOPE | Minimum requester capability required by the Master Brief; the core of the business need | Master Brief s.3, STK-001 | No
SCP-002 | Controlled category mechanism | IN SCOPE | Required capability; reporting in SCP-011 and triage in SCP-006 both depend on controlled categories rather than free text | Master Brief s.3, STK-004, STK-005 | No
SCP-003 | View status and history of own requests | IN SCOPE | Directly addresses the visibility problem identified in the scenario | Master Brief s.3, STK-001 | No
SCP-004 | Feedback when a request is accepted, rejected, updated or completed | IN SCOPE | Required capability; delivered as in-application feedback only (see SCP-014 for notifications) | Master Brief s.3, STK-001 | No
SCP-005 | Staff view of requests relevant to their authorisation | IN SCOPE | Required staff capability and the point at which authorisation becomes functional rather than administrative | Master Brief s.3, STK-002, STK-003 | No
SCP-006 | Search, filter and sort requests | IN SCOPE | Required staff capability; addresses the prioritisation difficulty described in the scenario | Master Brief s.3, STK-004 | No
SCP-007 | Assign or accept responsibility for a request | IN SCOPE | Required staff capability; implements the assignment model agreed in CFL-003 | Master Brief s.3, CFL-003 | No
SCP-008 | Controlled status transitions with recorded acting user | IN SCOPE | Required staff capability; the recorded actor is what supplies the accountability the current process lacks | Master Brief s.3, s.2, STK-005 | No
SCP-009 | Record actions, comments and resolution information | IN SCOPE | Required staff capability; creates the single controlled lifecycle record the scenario identifies as missing | Master Brief s.3 | No
SCP-010 | Resolve or close requests where authorised | IN SCOPE | Required staff capability | Master Brief s.3 | No
SCP-011 | Management view of open, overdue, resolved and closed requests by category and status | IN SCOPE | Required management capability; the reporting need behind CFL-001 | Master Brief s.3, STK-005 | No
SCP-012 | Authentication and role-based access control | IN SCOPE | Not listed as a business capability but made necessary by the CFL-002 resolution and CON-006; without it the restricted handling of security requests cannot be delivered | CFL-002, CON-006, STK-007 | Yes
SCP-013 | Native mobile application | OUT OF SCOPE | A responsive web interface satisfies the stated access need within CON-002 and CON-004. A native build adds a second toolchain, store release process and test matrix with no additional evidenced stakeholder benefit at M1. | CON-002, CON-004 | Yes
SCP-014 | Email or push notification of status changes | DEFERRED | Valuable to STK-001 but depends on a delivery service whose cost and free-tier limits are unknown until the platform decision in M2. In-application feedback (SCP-004) meets the minimum capability in the interim. | CON-003, DEC-003 | No
SCP-015 | Photograph attachments on a request | DEFERRED | Would materially improve fault triage, but introduces file storage cost, malware scanning and additional personal-information handling under CON-007. Deferred pending the platform and retention decisions. | CON-003, CON-007 | No
SCP-016 | Integration with existing campus systems (student records, HR, asset register) | OUT OF SCOPE | No evidence is currently available that institutional APIs exist or would be made accessible to a student project. Committing to an integration the team cannot verify would create unmanageable dependency risk. | CON-008, CON-002 | No
SCP-017 | Ingestion of requests from existing email, telephone or WhatsApp channels | OUT OF SCOPE | The business need is to replace fragmented channels with a single controlled record, not to federate them. Ingestion would preserve the duplication the platform exists to remove. | Master Brief s.2, s.2.1 | No
SCP-018 | Technician scheduling, rostering or workload balancing | OUT OF SCOPE | Not a stated capability and not raised by any identified stakeholder; would substantially expand the domain model under a fixed schedule | CON-001, CON-002 | No
SCP-019 | Multi-campus or multi-tenant operation | DEFERRED | Single-campus operation satisfies the current stakeholders. Recorded as deferred rather than excluded so that the M2 data model does not foreclose it unnecessarily. | CON-002 | No
SCP-020 | Automated enforcement of the data retention period | DEFERRED | The retention period itself is undecided (DEC-005). Automating enforcement before the rule exists would encode an unverified assumption. | CFL-004, DEC-005 | No
Baseline summary
In scope | 12
Deferred | 4
Out of scope | 4
Total items | 20

## constraints
Constraints
Fixed conditions on the project, what each one means for engineering, and where they pull against one another
ID | Category | Constraint | Source | Engineering implication | Interacts with | Trade-off summary
CON-001 | Scope | The delivered system must support the minimum requester, staff and management capabilities; committed scope is baselined and changed only through controlled change | Master Brief s.3, s.4 | Sets a floor that cannot be traded away under schedule pressure. Any additional feature must be justified against value and its effect on the other constraints, so the scope baseline becomes the reference for every later change request. | CON-002 | Fixed capability floor plus fixed schedule means quality or additional scope absorbs any pressure, not the minimum capabilities
CON-002 | Schedule | The project must progress through four formal milestones within the SEN381 delivery period, with M1 baselined before architecture decisions are made | Master Brief s.4, s.20 | Rules out exploratory or open-ended technology evaluation in M2. Favours technologies the team can already use productively, and forces requirements to be stable enough at M1 to support architecture decisions that follow immediately. | CON-004 | See CON-004: an unfamiliar stack costs learning time the schedule does not contain
CON-003 | Cost & resources | Free or low-cost services preferred where practical; free-tier limits and likely operational cost beyond the educational context must be identified | Master Brief s.4, s.18 | Free tiers commonly restrict backups, private networking, audit log retention and uptime guarantees. The hosting decision therefore cannot be made on price alone and must be evaluated against the security and quality constraints before it is committed. | CON-006, CON-007 | A free tier that lacks audit log retention conflicts directly with the accountability need behind CON-007; either the cost assumption or the retention approach must give
CON-004 | Cost & resources | Exactly three students, working part-time alongside other modules, with technology limited to what the team can realistically learn and support | Master Brief s.4, s.7.1, s.18.1 | Team capability is an engineering input, not a preference. Selecting an unfamiliar framework spends schedule on learning rather than on verification, and concentrates risk if only one member understands a component. | CON-002 | Familiar stack lowers schedule risk but may fit the requirements less well; the trade-off must be recorded in the M2 ADR rather than assumed
CON-005 | Quality | Quality attributes must be defined measurably in M1 and later supported by test and measurement evidence; unsupported quality claims are not accepted | Master Brief s.4, s.15 | Every NFR written now creates a later obligation to produce evidence. Vague quality language cannot be verified, so NFRs must carry numbers and conditions from the outset or they will be unusable in M3. | CON-002 | Each measurable NFR adds verification work in M3; the number of NFRs is itself a schedule decision
CON-006 | Security | Security is a lifecycle-wide responsibility; secrets must not be committed; trust boundaries, authentication, authorisation and least privilege must be addressed from requirements onward | Master Brief s.4, s.16 | Rules out deferring authorisation to late construction. The restricted visibility agreed in CFL-002 requires role-based access control, which is an architecture-level concern and must be treated as an architecturally significant requirement in M2. | CON-003 | Some security controls (private networking, log retention, managed identity) are paid features on platforms that are otherwise free
CON-007 | Security | The system handles personal information of students and staff and must comply with applicable data protection obligations under POPIA | Campus context; STK-009 | Constrains what may be captured, who may view it, how long it is retained and whether access is auditable. Data minimisation directly limits the reporting richness sought in CFL-001 and CFL-004. | CON-003, CON-001 | Retention and audit requirements may exceed what a free-tier platform provides; see CON-003
CON-008 | Cost & resources | Belgium Campus does not guarantee that a chosen language, framework, service or deployment platform is available or supported on the BC Desktop platform or institutional environment | Master Brief s.25 | Compatibility must be verified before the technology is committed, not after. Creates a real risk that a technically sound choice is undeliverable in the available environment, so the M2 decision needs evidence of availability, not only suitability. | CON-002, CON-004 | Verification costs schedule time in M2; skipping it risks rework that costs far more
Constraints by category
Scope |  | 1
Schedule |  | 1
Cost & resources |  | 3
Quality |  | 1
Security |  | 2
Total |  | 8

## decision-log
Decision Log
Decisions and deferments taken during M1, the alternatives weighed, and what each one commits or blocks downstream
ID | Date | Decision or deferment | Alternatives considered | Rationale | Consequences / downstream impact | Evidence still required (if deferred) | Owner | Status
DEC-001 | 2026-09-06 | Scope CivicConnect to a campus / educational institution context | Municipality or local government; community NGO; residential estate | The Master Brief does not name the client organisation. The request types listed in s.2 (facility faults, IT support, lost property, security concerns) correspond to an institutional campus. A recorded assumption is preferable to proceeding with an ambiguous stakeholder set. | Determines the entire stakeholder register and the applicability of POPIA (CON-007). If the assumption is wrong, STK-001 to STK-009 and every derived requirement must be revisited. | — | A | DECIDED
DEC-002 | 2026-09-06 | Defer selection of the technology stack | Commit now to a familiar stack; commit now to a stack chosen for requirement fit | M1 is explicitly not a technology-selection milestone. The requirements baseline is not yet complete, so no evidence currently distinguishes the alternatives. | Preserves M2 options. Creates a dependency: the M2 decision must satisfy CON-004 (team capability) and CON-008 (institutional environment availability) as well as requirement fit. | Completed FR/NFR baseline; verification that candidate stacks are available on the BC Desktop platform | A | DEFERRED
DEC-003 | 2026-09-06 | Defer selection of the hosting and deployment platform | Commit to a free-tier platform now; commit to a paid platform now | The cost constraint (CON-003) favours a free tier, but free tiers commonly omit audit log retention, backups and private networking, which CON-006 and CON-007 require. The decision cannot be made on price alone and no platform research evidence exists yet. | Blocks SCP-014 and SCP-015, both of which depend on platform capability and cost. Must be resolved before the M2 architecture is finalised. | Documented free-tier limits for candidate platforms, covering audit log retention, backup and likely operational cost beyond the educational context | A | DEFERRED
DEC-004 | 2026-09-06 | Treat role-based access control as an architecturally significant requirement | Handle authorisation as an application-level concern during construction; use a single shared staff view | The CFL-002 resolution restricts security-request visibility by role. Authorisation applied late cannot be retrofitted cleanly across every view and transition, and CON-006 requires it to be addressed from requirements onward. | Constrains the M2 architecture and data model. Adds verification obligations in M3 under CON-005. | — | A | DECIDED
DEC-005 | 2026-09-06 | Defer the personal-information retention period | Retain indefinitely; adopt an arbitrary fixed period | CFL-004 is unresolved. The lawful period depends on guidance from STK-009 that the team does not yet have, and an arbitrary figure would be an unverified claim under CON-007. | SCP-020 (automated retention enforcement) is deferred as a consequence. Affects the M2 data model, since aggregated statistics must survive deletion of identifiable data. | Retention guidance from the information officer, or a documented institutional retention standard | A | DEFERRED
DEC-006 | 2026-09-06 | Limit mandatory capture fields at submission to category, location and description | Capture full structured detail at submission; make all detail optional | Resolution of CFL-001. Minimal mandatory capture protects submission speed for STK-001; category remains mandatory because the SCP-011 reporting depends on it. | Reporting richness for STK-005 depends on post-submission detail being supplied. If uptake is poor, this decision may need revisiting through change control. | — | A | DECIDED
DEC-007 | 2026-09-06 | Exclude a native mobile application from the committed scope | Native mobile in addition to web; native mobile instead of web | A responsive web interface meets the access need within CON-002 and CON-004. A second build and release path is not supportable by three part-time students within the delivery period. | Places a usability obligation on the web interface for mobile viewports, which becomes a quality attribute for Member B to specify measurably under CON-005. | — | A | DECIDED
Decision status
Decided |  | 4
Deferred — evidence outstanding |  | 3
Total logged |  | 7