## Decision Log
Decision Log
Decisions and deferments taken during M1, the alternatives weighed, and what each one commits or blocks downstream
ID | Date | Decision or deferment | Alternatives considered | Rationale | Consequences / downstream impact | Evidence still required (if deferred) | Owner | Status | Decision status
DEC-001 | 2026-09-06 | Scope CivicConnect to a campus / educational institution context | Municipality or local government; community NGO; residential estate | The Master Brief does not name the client organisation. The request types listed in s.2 (facility faults, IT support, lost property, security concerns) correspond to an institutional campus. A recorded assumption is preferable to proceeding with an ambiguous stakeholder set. | Determines the entire stakeholder register and the applicability of POPIA (CON-007). If the assumption is wrong, STK-001 to STK-009 and every derived requirement must be revisited. | — | Ethan | DECIDED | Decided | 7
DEC-002 | 2026-09-06 | Defer selection of the technology stack | Commit now to a familiar stack; commit now to a stack chosen for requirement fit | M1 is explicitly not a technology-selection milestone. The requirements baseline is not yet complete, so no evidence currently distinguishes the alternatives. | Preserves M2 options. Creates a dependency: the M2 decision must satisfy CON-004 (team capability) and CON-008 (institutional environment availability) as well as requirement fit. | Completed FR/NFR baseline; verification that candidate stacks are available on the BC Desktop platform | Ethan | DEFERRED | Deferred — evidence outstanding | 3
DEC-003 | 2026-09-06 | Defer selection of the hosting and deployment platform | Commit to a free-tier platform now; commit to a paid platform now | The cost constraint (CON-003) favours a free tier, but free tiers commonly omit audit log retention, backups and private networking, which CON-006 and CON-007 require. The decision cannot be made on price alone and no platform research evidence exists yet. | Blocks SCP-014 and SCP-015, both of which depend on platform capability and cost. Must be resolved before the M2 architecture is finalised. | Documented free-tier limits for candidate platforms, covering audit log retention, backup and likely operational cost beyond the educational context | Ethan | DEFERRED | Total logged | 10
DEC-004 | 2026-09-06 | Treat role-based access control as an architecturally significant requirement | Handle authorisation as an application-level concern during construction; use a single shared staff view | The CFL-002 resolution restricts security-request visibility by role. Authorisation applied late cannot be retrofitted cleanly across every view and transition, and CON-006 requires it to be addressed from requirements onward. | Constrains the M2 architecture and data model. Adds verification obligations in M3 under CON-005. | — | Ethan | DECIDED
DEC-005 | 2026-09-06 | Defer the personal-information retention period | Retain indefinitely; adopt an arbitrary fixed period | CFL-004 is unresolved. The lawful period depends on guidance from STK-009 that the team does not yet have, and an arbitrary figure would be an unverified claim under CON-007. | SCP-020 (automated retention enforcement) is deferred as a consequence. Affects the M2 data model, since aggregated statistics must survive deletion of identifiable data. | Retention guidance from the information officer, or a documented institutional retention standard | Ethan | DEFERRED
DEC-006 | 2026-09-06 | Limit mandatory capture fields at submission to category, location and description | Capture full structured detail at submission; make all detail optional | Resolution of CFL-001. Minimal mandatory capture protects submission speed for STK-001; category remains mandatory because the SCP-011 reporting depends on it. | Reporting richness for STK-005 depends on post-submission detail being supplied. If uptake is poor, this decision may need revisiting through change control. | — | Ethan | DECIDED
DEC-007 | 2026-09-06 | Exclude a native mobile application from the committed scope | Native mobile in addition to web; native mobile instead of web | A responsive web interface meets the access need within CON-002 and CON-004. A second build and release path is not supportable by three part-time students within the delivery period. | Places a usability obligation on the web interface for mobile viewports, which becomes a quality attribute for Member B to specify measurably under CON-005. | — | Ethan | DECIDED
DEC-008 | 2026-09-08 | Adopt a two-stage protected branching model: feature branches merge to dev, dev merges to main only at a release or baseline point. Both branches protected with two required approvals. | Trunk-based development with feature branches directly to a single protected main; full GitFlow with release and hotfix branches | Keeps main as a clean controlled product state matching Master Brief s.9, while allowing integration work to accumulate in dev without repeatedly disturbing the controlled baseline. Full GitFlow adds release and hotfix branches that three students on a single delivery stream do not need. | Every substantive change requires two approvals at two merge points, so integration is slower and both teammates gate every change. main will lag dev, so baseline evidence must be explicitly merged and tagged at each milestone rather than assumed present. | — | Ethan | DECIDED
DEC-007 (Revised) | 2026/09/06 - Revised 2206/09/09 | Exclude a native mobile application from the committed scope; mobile access is delivered through responsive web | Native mobile in addition to web; native mobile instead of web | Originally taken as a team judgement: a responsive web interface meets the access need within CON-002 and CON-004, and a second build and release path is not supportable by three part-time students within the delivery period. Revised 09/09/2026 — the client confirmed verbally that the solution is to be a web application with mobile access via responsive web (CON-011). The decision is unchanged; its basis is now a client directive rather than a team judgement. | Places a usability obligation on the web interface at mobile viewports, to be specified measurably by Member B under CON-005. Following the revision, the exclusion is no longer a team preference and cannot be revisited without a change request under Master Brief s.14. Reduces the risk that scope pressure later reopens the question. | — | Ethan | DECIDED
DEC-009 | 2026-09-09 | Adopt a controlled process for capturing verbally-issued client requirements: instructions given in session are recorded in dated team notes by a nominated member, committed to the repository within one working day, and confirmed with the client at the next session before being treated as binding. | Rely on individual members' personal notes; request that all client instructions be issued in writing; treat verbal instructions as non-binding until they appear in a written brief. | The client (STK-010) issues requirements verbally in sessions with no written record on their side. Without a controlled capture process, a directive exists only in individual memory, cannot be traced to a source, and cannot be shown to have been the basis of a requirement or constraint. Requesting written instruction was rejected as outside the team's control. Treating verbal instruction as non-binding was rejected because the instructions are directive in practice and ignoring them would put delivery at risk. Confirming at the next session gives the client an opportunity to correct a misheard or misrecorded instruction before it propagates into requirements. | Creates a recurring obligation for the duration of the project, not a one-off task. Introduces up to a one-session lag between an instruction being given and it being treated as binding, which is a deliberate accuracy-over-speed trade-off. Every constraint or requirement derived from a verbal instruction must cite the dated note as its source, so the notes become a controlled artefact subject to the same repository controls as any other. Reduces the risk of disputed or forgotten requirements at later milestones. | — | Ethan | DECIDED